EXECUTIVE SUMMARY

INTRODUCTION

A concise description of the Madibeng Local Municipality is set out below.

Madibeng is classified as a category B Municipality, functioning through the Executive Mayoral System.  The Municipality was recently demarcated into 41 wards and the Municipal Council comprises of 82 Councillors, (of which 10 are members of the Mayoral Committee), with a full-time Speaker, Chief Whip and Executive Mayor.

Madibeng consists of several urban and rural areas, 9 000 farm portions, as well as a proper established and serviced industrial area.  According to the Municipal VTSD plan there are 43 villages, 6 Townships and 7 small dorpies.

The following Traditional Authorities are situtated within the jurisdiction of Madibeng.

Mmakau Tribal Office

Baapo ba Mogale Tribal Office, Bapong

Bakwena ba Mogopa, Jericho

Bakwena Ba Mogopa Tribal Office,  Hebron

Batang Tribal Office Maboloka

One of the advantages of Madibeng is its central location in the North West Province, with Pretoria, Johannesburg, Rustenburg and Krugersdorp as bordering neighbours. As the neighbouring towns are easily accessible through road networks, residents are not confined to employment in the Madibeng jurisdiction alone, but can easily commute to workplaces in the cities and other towns. Furthermore the Lanseria Airport is situated a mere 40 kilometers from Brits.

IDP PROCESS PLAN

The 2020/21 IDP and Budget Process Plan, used as framework in the reviewing process, was adopted by Council on 27 August 2019 per resolution ADMIN.0017.

THE STRUCTURE OF THE IDP DOCUMENT

The structure of the IDP document is divided in 5 phases, ie.

- Analysis

- Strategy

- Project

- Integration

- Approval

Analysis Phase

The phase covers the following areas:

Location and Extent, Socio Economic Aspect, whereby the statistical overview of the Municipality has been analysed as per sectors.  Municipal Organizational Structure that covers both Political and Administrative issues. Other important aspects include Municipal Policies, Plans and Bylaws, Strengths, Weaknesses, Opportunities and Threads (SWOT) Analysis, Organizational Risks and Comments of the Auditor General’s Report.

The Municipality has implemented a Performance Management System whereby progress is monitored by the conducting of performance assessments on a quarterly, mid year and annual basis.  Performance audits are conducted by both the Internal Auditors and Auditor General and the Performance reports are also published in the Annual Report.

Strategy Phase

The key aspects in this phase are Public and Stakeholder Participation in the IDP Review processes, Ward Needs and Prioritized Municipal Wide Needs, which were determined at an IDP Representative Forum meeting held on 19 November 2019 as follows

| Priority 1 : Priority 2 : Priority 3 : Priority 4 : Priority 5 : Priority 6 : | Water and Sanitation Roads and Stormwater Electricity Land and Housing Social Services Local Economic Development |
| --- | --- |

The Vision which is “Madibeng, the prosperous platinum and green tourism city”, Mission and Values, Objectives and Strategies.  The Strategies, amongst other, focuses on the following Key Performance Areas of Local Government, ie; Local Economic Development, Financial Viability and Basic Service Delivery and Infrastructure issues.

The following information on services in Madibeng is based on STATSSA (Census 2011) figures:

| TOTAL NO OF HOUSEHOLDS : 160 722 |  |  |  |
| --- | --- | --- | --- |
| SERVICE LEVEL | WITH ACCESS | BACKLOG |
| Water Supply | 143 224 | 17 500 |
| Sanitation | 120 269 | 40 428 |
| Electricity | 130 164 | 30 560 |
| Waste Management | 83 628 | 77 096 |
| Housing | 120 269 | 64 463 |

Project Phase

The project phase is the nuts and bolts of IDP implementation.  The phase covers the Prioritized Projects for the period 2020/21 and 2021/22 which is the closing cycle of the current 5 Year Plan.  Progress on Prioritized Projects and Sector Department Projects for alignment purposes with Spheres of Government.

Integration Phase

The Phase focuses on Twelve Municipal Sector Plans, Performance Management System and Framework and Summary of Alignment with National Plans and Strategies.  This includes, amongst other, The National Development Plan and Medium Term Strategic Framework.

Approval Phase

Conclusion is covered under this phase.

ANALYSIS PHASE

KPA : TRANSFORMATION AND ORGANISATIONAL DEVELOPMENT

1.1. LOCATION & EXTENT

The two main economic contributing areas within the Madibeng Local Municipality are Brits and Hartbeespoort Areas.  The natural hydrology of Madibeng presents economic opportunities along the water bodies. There is increased pressure of residential developments along the Hartbeespoort Dam and the Rooikoppies Dam.  The former has experienced the development pressure for longer than the latter.  This is due to the scenic natural settings around the dams.  The rivers on the other hand experience agricultural activity due to the favouring conditions on the river banks and areas within their proximity.

1.1.1.	BRITS

Brits Town Precinct is situated within Madibeng Local Municipality north of Hartbeespoort Dam and adjacent to N4 Bakwena-Platinum Highway intersection. Brits Town occupies an area of 54,47 km2 of the total of 3,839 km2 of Madibeng Local Municipality.  The town area consists of the following areas:

Town of Brits with the inclusion of the Central Business District

Residential neighbourhood of Elandsrand

Primindia

Brits Industrial Area

The remote townships of Oukasie, Damonsville and Mothutlung; and

The farm portions in-between these areas.

The Brits Town Area is the key economic as well as governance centre within the Madibeng Local Municipality.  Brits is located in close proximity to key urban centres in Gauteng and 65 km from Rustenburg. This area is linked to both Rustenburgh and Gauteng urban centres by N4 Bakwena-Platinum Highway.

The area is physically and functionally interconnected to the northern parts of Tshwane through a group of villages, such as Mmakau, stretching eastwards from Mothutlung up to Ga-Rankuwa.  Formal residential developments are found in Lethlabile located north of Brits and Mothutlung in the easterly direction of Brits town.

1.1.2. 	HARTBEESPOORT

Hartbeespoort is located on the boundary between Gauteng and North West Province.  The Precinct is in close proximity to and with good connectivity to key urban areas in Gauteng such as Pretoria, Sandton, Randburg, Midrand and Krugersdorp and is 65 km from Rustenburg.  This area is linked to both Rustenburg and Gauteng urban centres by N4 Bakwena-Platinum Highway.  From a regional tourism perspective the area is close to Lanseria International Airport which offers both domestic and international flights in Gauteng.  This area consists of places around Hartbeespoort Dam in Madibeng Local Municipality and extends to approximately 180 km2.

Hartbeespoort is characterized by residential development such as Schoemansville, Ifafi, Meerhof and Kosmos.  Residentail areas are very distinct from those in Brits.  The Magaliesberg Mountain Range topographically separates these two areas.  Towards the South of the mountain range there are high income estates and resorts which cater for up-market lifestyles.  The residential area include but are not limited to golf courses, nature reserves, marinas and security control.  These areas include the likes of Pecanwood, Birdwood, Xanadu to mention but a few.

1.1.3. 	RURAL AND FARMING AREAS

In rural areas, access to services, land, income and livelihoods contributes to the depiction of the municipal human resources and thus influence the rate of rural development. Rural areas are characterised by sparsely populated residential units. Similar and even further scattered settlements can be found in remote agricultural and farm units. These types of settlements can be found in the easterly direction of the municipal area. These areas include Oskraal, Madinyane, Klipvoordam  and  Kilpvoorstad.  These settlements are characterised by subsistence farming.

Located on the east side of Schoemansville and South of the Magaliesberg mountain range is the agricultural holding of Melodi. This areas unlike the rest who are subsistence farming rural areas, it purpose is to foster rural living lifestyle. This is attributed by the affluent households it hosts.

1.1.4.	NUCLEAR AREA

The Pelindaba Nuclear Plant facilitates nuclear activity for the state. It is located on the South Eastern side of the municipal area and it has a 5 km restricted development buffer zone.

1.1.5. 	MAPS OF MADIBENG

1.1.6.  WARD DESCRIPTION OF AREA

| WARD | AREA |
| --- | --- |
| Ward 1 | Atlanta, Fafung, Kwarriekraal, Klipvoorstad, Legonyane, Mmasebolane, Rasai, Rooival, Sephai, and Vaalboschsloot, |
| Ward 2 | Jericho and Mmupudung |
| Ward 3 | Madidi and Lekgema |
| Ward 4 | Maboloka, Bafokeng and Bataung |
| Ward 5 | Maboloka, Bafokeng and Bataung |
| Ward 6 | Maboloka |
| Ward 7 | Majakaneng |
| Ward 8 | Klipgat: Stakaneng; Jakalasdans, Msiza Village, Mboneni, Selepe, Ndlovu, Ngobeni |
| Ward 9 | Letlhabile Block B, C, and part of Block H |
| Ward 10 | Kgabalatsane, Phiring, Phuting, Rockville, Kagisanong, Micha-Kgasi, Greenside, Magaseng, Mmotong, Itireleng and Kgola |
| Ward 11 | Lethlabile Block I, Block G, Zone 16, Ext. 2 and Block B Ext.1 |
| Ward 12 | Lethlabile Zones 2, 5, 6, 8, 10, 12, 14 and Block F |
| Ward 13 | Oukasie |
| Ward 14 | Mosholozi Portion 455 Kameeldrift farm 211 JQ, Rashoop, Wonderpark and Oukasie Ext. 5 |
| Ward 15 | Hebron, New Stand, Moagi, Phase 1 and Phase 2 Itsoseng |
| Ward 16 | Itsoseng, Hebron (Roma Section), Matshelapata |
| Ward 17 | Polonia, Rampogodu, Jalasdown, Mangopeng, Mapetla |
| Ward 18 | Mmakau, Thetele, Switch, New Town , Mashiapere, Tlhopane, Block 7, Ramalapong, Naledi |
| Ward 19 | Tshwara, Springs, Channelview, Blackrock, Mathathaneng, Moumong, Dekroon, Moagi and Newtown |
| Ward 20 | Mothotlung |
| Ward 21 | Damonsville, Zilkaatsnek, De Kroon, Mothotlung Ext. 1 & 2, |
| Ward 22 | Brits Town from Hendrik Verwoerd Ave up to the water canal bordering Elandsrand, Portion of Oukasie, i.e. Greenside, Block 5, Phase 2, Phase 3 B & C, Corrie Sanders, Siyathlathla, Masengkeng, Noordkamp and New Clare |
| Ward 23 | Brits CBD, Primindia |
| Ward 24 | Klipgat A, B & C, Hillside, Ikageng, 2010, Sofasonke, Tophasa, Ndlovu, Phasa, Mashamoplame |
| Ward 25 | Bokfontein, Legalaopeng, Marulakop, New Town, Rantene, Bapong, Oustad and Skoolplaas |
| Ward 26 | Wonderkop and Ext. 2 |
| Ward 27 | Mooinooi, Bokamoso, Loekeng |
| Ward 28 | Mesetlheng, Schandav, Legalaopeng, New Town, Petlele, Modikoane, Riverside, No.1, Bapong |
| Ward 29 | Kosmos, Poland, Shamburg, Orange Farm Sangiro, Kommandonek, Skeerpoort, Hartbeeshoek |
| Ward 30 | Meerhof, Ifafi, Melodie, Refentse, Sunway Village, Ten Rooms, Rietfontein, Hartbeespoort |
| Ward 31 | Majakaneng, Sereopark, Safropa, Modderspruit, Mangoes, Thabeng, Skierlik & Katlegong |
| Ward 32 | Wonderkop, New Stand, Segwaelane |
| Ward 33 | Wawiel, Shieling Farm, Mahantjie, Schoemansville and Damdoryn |
| Ward 34 | Shakung, Shakunyaneng, Moiletswana, Madinyane, Baikagedi, Ramogatla, Letlhakaneng, Rietview, Dimpongpong |
| Ward 35 | Kgabalatsane, Morolong, Oskraal and Rabokala, Thetele, Switch, Rankotea, Ntswapilong |
| Ward 36 | Klipgat |
| Ward 37 | Klipgat, Ikageng, 2010, Hillside and Langalibalele |
| Ward 38 | Centreville, Block E, F & H, Plots Oskraal, Zone 6 & 10, Skierlik |
| Ward 39 | Elandsrand, Oukasie – Vuka Section, Mamogalieskraal |
| Ward 40 | Pansdrift, Sonop, Khalamtwana, Part of Segwaelane, Geluk, Uitvalgrond, Kareepoort, Losperfontein, Rooikoppie and Regorogile |
| Ward 41 | Moseja Section, Beverley Hills, Block E, Motseng and Midas Section |

1.2. SOCIO ECONOMIC PROFILE

PRIMARY ECONOMY

Agriculture,   Tourism   and   mining   are   the   main   primary   economies.   The Agricultural sector, which produces food, is the biggest primary economy. It is categorized into four classifications, namely, extensive farming (44% of the Municipal   area),   intensive   agriculture   (18%),   game   farming   (10%)   and subsistence farming. Tourism also plays a major economic role as it is based on the natural  systems  (11%).  Scenic routes, heritage sites, resorts and  nature reserves are some of the main attractions in the tourism sector.

The mining sector is dominated by platinum and chromium mining as well as quarrying activity. Platinum mining activity is located on the south eastern side of the side of Brits while quarrying is spread around the municipal area. The primary economic activities have to be managed in such a manner as to make sure that their impact on the natural environment and resources is controlled.

SECONDARY ECONOMY

Secondary economy refers to activities involved in the manufacturing of finished goods. The secondary sector is understood to include all manufacturing, processing, and construction. Activities associated with the secondary economy include metal working, smelting, automobile production, textile production, chemical industries, engineering industries, manufacturing, energy utilities, breweries, bottlers, and construction.

Secondary economic activities are normally linked to the primary economic activity. Thus secondary activity in Madibeng Local Municipality is in alignment with agricultural processing without the exclusion of manufacturing and construction. These activities are located in Brits, along the N4 Highway as well as a lesser activity scale in Lethlabile.

TERTIARY ECONOMY

The tertiary sector of the economy is largely associated with service industries. This sector provides services to both the general population and businesses. Activities that are commonly associated with tertiary economy include retail and wholesale sales, transportation, distribution, entertainment, restaurants, clerical services, media, tourism, insurance, banking, healthcare and law.

In most developed and developing countries, a growing proportion of workers are devoted to the tertiary sector. The N4 Highway plays a significant role within the transport, logistics and distribution activities within the municipal area. The N4 facilitates transport linkages between Rustenburg, Tshwane and Johannesburg.

Brits  is  the  administrative  capital  of  the  municipality,  bearing  the  bulk  of municipal and government services. The Pelindaba nuclear facility also forms part of the government services. It is located on the south eastern side on the municipal area.

DEMOGRAPHIC INDICATORS

The ability of individuals to contribute to production is largely dependent on their level of human capital development. This level of development is indicated by demographic indicators such as education, housing, employment and income levels.

Education and formal training play an important role in the overall value of people.  Increased value of Madibeng  Local  Municipality’s  residents  can improve their living conditions. Further Education Training (FET) colleges, which concentrate on economic sectors present in the Municipality, will improve the human capital in Madibeng. This will reduce unemployment rate in the Municipality.

RURAL DEVELOPMENT

The north eastern quadrant of the Municipality is composed of rural settlements (villages). These villages are characterised by subsistence farming and indigenous knowledge systems. Rural development can be assessed by investigating rural livelihoods, access to income, access to land and access to services. This will inform the manner in which basic services are provided and the rural landscape is retained.

Rural areas are characterized by relatively high logistical costs and high per capita service costs. Therefore the provision of government services such as the municipal office, clinic, schools, become costly. Thus in cases where services are provided, the recurrent costs of all but the most basic services must be met by those who use them. It is essential for Madibeng to recover costs in the peril- urban and rural areas through the pro-active debt collection policies.

The process of formalising settlements in rural areas is essential. This process helps to unlock the economic potential of the area, facilitate appropriate regulation of land use as well as enable the municipality to implement cost recovery. This will ensure sustainable rural settlements.

STATISTICAL OVERVIEW

2017 IHS MARKIT REGIONAL EXPLORER VERSION  1417

According to the statistical information received from IHS Market, Madibeng Local Municipality housed apprioxinately 1.0% of the country’s total population in 2017.  The Municipal growth rate between 2007 and 2017 was 3.14% in comparison to the 1,56% of South Africa as a whole.

The following two Population graphs were based on the official STATS SA figures and those submitted by IHS Markit:

Madibeng Local Municipality has significantly more males than females with a population split of 113.2 males per 100 females.

Source: IHS Markit Regional eXplorer version 1417

STATISTICS FOR MADIBENG AS PER 2011 CENCUS:

| Population Size Census 1996 Census 2001 Census 2011 | 319 974 347 578 477 381 | Population group Black African Coloured Indian or Asian White | 426 192 4 292 2 445 42 691 |
| --- | --- | --- | --- |
| Average annual Growth Rate | 3.17% | Population (Area km²) | 3839 |
| Population density | 124 per km² | Sex Ratio (Males/100 Females) | 114 |
| Number of Households | 160 724 | Dependency ration | 0.44 |
| Average Household Size | 3.00 | Female headed hh | 30.3% |
| Gender Distribution: Male Female | 53% 47% | Age Distribution/ Structure: Young ( 0-14 Years) Working age (5-65 Years) Eldery (Older than 65 Years) | 25.70% 69.20% 5.10% |
| Employment Status - Persons 15 to 65 Years of Age: Employment Unemployment Youth Unemployment(15-34) | 69.60% 30.40% 38.20% | Monthly Income levels: No Income Income up to R800 Income between R800-R 6500 Income above R6500 | 23.3% 27.3% 43.3 6.3% |
| Education levels - Persons Older Than 20 Years: No Schooling Some Primary to Secondary Schooling Grade 12 Higher | 7.80% 57.30% 7.30% 27.60% | Flush toilet connected to sewerage | 27.2% |
|  |  | Electricity for lighting | 81% |
|  |  | Piped water inside dwelling | 22.2% |
| Formal dwellings | 59.2% | Weekly refuse removal | 25.7% |
| Housing owned/paid off | 54.1% | Agricultural hh | 23,621 |
| HIV 45.5% compared against North West Province prevalence rate of 26.7% |  |  |  |

MORE DEMOGRAPHICS

Please note that statistics on the respective categories of service delivery, ie. water and sanitation, electricity, housing and land use management are reflected under the chapter Basic Service Delivery on pages 104 TO 157

1.3.  POLITICAL  ORGANOGRAM

Cllr W Modiba

Cllr JD Smith

\

1.4 ADMINISTRATIVE STRUCTURES

DEPARTMENTAL INFORMATION

PC

CORE FUNCTIONS

NAME OF DIRECTOR

DEPARTMENTS

Revenue; Expenditure and Supply Chain Management; Budget and Reporting

1

Budget and Treasury Office

L. Mere

Acting CFO

2

MG Magole

Director

Corporate Support Services

Human Resource Management and Training; Administration; Records and Secretariat Services

N. MAAPE

ACTING MUNICIPAL MANAGER

3

Economic Development and Planning

Agriculture, Tourism, SMME

S Mnisi

Director

Human Settlement and Planning

4

N Pule

Acting Director

Housing, Land Administration, Town Planning, Urban Renewal and  Building Control

Community Services

M Mmope

Director

5

Solid Waste and Environmental Management; Parks, Sports and Recreation, Arts and Culture

Public Safety and

Social Development

P Dilinga

Director

6

Security, Traffic, Clinics, Fire

Project Management Unit, Water, Sanitation, Electricity, Roads and

Stormwater

7

Technical Services

M. Church

Acting Director

8

Intergovernmental Relations, Communications, Offices of the Executive Mayor, Speaker,

Chief Whip, MPAC, Audit, Risk Management, IDPand PMS,

and Legal Services

MP Raputsoa

Deputy Director

Office of the Municipal Manager

DESCRIPTION OF PORTFOLIO COMMITTEES

| PC 1 Financial Committee | PC 2 Corporate Services Committee | PC 3 Economic Development Committee |
| --- | --- | --- |
| PC 4 Planning Committee | PC 5 Community Services Committee | PC 6 Social Services and Safety Committee |
| PC 7 Infrastructure Committee | PC 8 IDP, PMS, and Legal Committee | PC 9 IGR and Communications Committee |
| PC 10 Traditional Affairs & Special Programmes Committee |  |  |

SECTION 79 COMMITTEES

The following standing committees were established in terms of section 79 of the Local Government: Municipal Structures Act, 1998 (Act No 117 of 1998)

| COMMITTEE | CHAIRPERSON |
| --- | --- |
| Municipal Public Accounts Committee (MPAC) | Councillor ED Diale |
| Rules Committee | Councillor KS Ntshabele |
| Petitions and Civilians Committee | OD Marapyane |
| Delegations Committee | HB Mathibela |

TRADITIONAL AUTHORITIES

The following Traditional Authorities are situtated within the jurisdiction of Madibeng:

Mmakau Tribal Office

Baapo ba Mogale Tribal Office, Bapong – Serving on the Council

Bakwena ba Mogopa, Jericho

Bakwena Ba Mogopa Tribal Office, Hebron

Bataung Tribal Office Maboloka

ROLEPLAYERS WITHIN MUNICIPALITY

Madibeng Council

### Mayoral Committee

Portfolio Committee’s

Ward Councillors

Municipal Manager

Tribal Authorities

Community Development Workers

Officials

ESTABLISHED FORUMS IN MADIBENG

The Business Consultative Forum, is constituted by delegates of Business Sector, Industrialists, Tourism Sector, Council Members, Mining Forum, Heads of Departments and the Municipal Manager. The Forum is chaired by the Executive Mayor and meets monthly.

The Mining Forum is constituted by representatives of all mining houses, councillors and officials

### The IDP Representative Forum consists of IDP Stakeholders, i.e. representatives of the following sectors:

Agriculture, Banking, Business, Health, Housing, Land, Mining, Transport & Water. Municipalities within Bojanala Platinum District Municipality region, CBO’s and Support Groups, SAPS, Trade Unions & Youth Forums, the District Municipality, National and Provincial Government, Traditional Authorities, Professional Service Providers, members of communities and residents.

INTERNAL AUDIT COMMITTEE

Madibeng Municipality has a functional Internal Audit Committee. The Audit Committee was established in December 2004.   The current committee members were appointed by the Council on 28 August 2018.  The Audit Committee comprises of five (5) external members, namely:

Me. FJ Mudau – Chairperson

Mr J Matsho – Member

Mr. VK Chuene – Member

Mr LC Mohalaba – Member

Mr FM Mkhabela – Member

Audit Committee Meetings are held quarterly, with the authority to convene additional special meetings as circumstances require, ensuring that the Audit Committee discharge its responsibilities found in its Charter.

PERFORMANCE REVIEW

To measure, monitor and evaluate the Municipality’s performance the Council has adopted the Balance Scorecard System. The Key Performance Areas, Key Performance Indicators and Performance Targets, which form part of the 5 Year IDP, are being used as the basis for the review of the municipal PMS and Performance Contracts of Senior Managers. Alignment between the IDP, PMS and budget is done through the projects that form part of the performance targets.

HUMAN RESOURCE INFORMATION

Organizational Structure

| VACANCY RATE 2018/19 |  |  |  |
| --- | --- | --- | --- |
| DESIGNATIONS | TOTAL APPROVED POSTS NO. | VARIANCES (total time that vacancies exist using fulltime equivalents) no. | VARIANCES (as a proportion of total posts in each category) % |
| Municipal Manager | 1 | 1 | 100% |
| Chief Financial Officer | 1 | 1 | 100% |
| Other Section 56 Managers | 8 | 1 | 87.5% |
| Managers | 41 | 13 | 32% |
| Professionally Qualified And Experienced Specialists And Mid-Management | 304 | 192 | 63% |
| Skilled Technical And Academically Qualified Workers-Junior Management- Supervisors- Foremen- And Superintendents | 405 | 224 | 55% |
| Semi-Skilled And Discretionary Decision Making | 483 | 253 | 52% |
| Unskilled And Defined Decision Making | 732 | 536 | 73.2% |
| TOTAL | 2086 | 1333 | 63.9% |

The Council adopted a new organisational structure in May 2018 and, although it was not active for the entire reporting period, it was nevertheless utilised for this purpose.  It thus might have an impact on comparisons with previous years

| TOTAL EMPLOYEES STAFF COMPLIMENT + VACANCIES |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| /19DESCRIPTION | 2017/18 | 2018/19 |  |  |  |
|  | Employees No. | Approved Posts No. | Employees No. | Vacancies No. | Vacancies % |
| Municipal Manager | 54 | 105 | 59 | 45 | 43 |
| Chief Audit Executive | 12 | Included in MM |  |  |  |
| Directorate: IDP/PMS/Legal Services | 35 | Included in MM |  |  |  |
| Corporate Support Services | 76 | 77 | 47 | 29 | 38 |
| Budget & Treasury Office | 160 | 146 | 106 | 39 | 27 |
| Infrastructure & Technical Services | 665 | 635 | 302 | 339 | 53 |
| Human Settlement & Planning | 71 | 71 | 36 | 35 | 49 |
| Economic Development, Tourism & Agriculture | 45 | 45 | 26 | 18 | 40 |
| Public Safety, Fllet & Facilities Management | 408 | 481 | 307 | 41 | 9 |
| Community Services | 449 | 526 | 446 | 77 | 15 |
| TOTALS | 1975 | 2086 | 1329 | 623 | 30% |

| TURN-OVER RATE |  |  |  |
| --- | --- | --- | --- |
| Details | Total Appointments as of Beginning of Financial Year | Terminations During the Financial Year | Turn-Over Rate |
| 2016/2017 | 95 | 52 | 2.9 |
| 2017/2018 | 42 | 56 |  |
| 2018/2019 | 383 | 44 | 12 |

### Departmental Equity Information

| Department |  | No of Males |  |  |  | No of Females |  |  |  |  | Foreign Nat. |  | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | A | C | I | W | D | A | C | I | W | D | M | F |  |
| Top Management | 5 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 8 |
| Snr Management | 24 | 1 | 0 | 1 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 36 |
| Prof. qualified and experienced specialists and mid management | 68 | 0 | 0 | 6 | 1 | 50 | 0 | 0 | 6 | 0 | 0 | 0 | 130 |
| Skilled technical academically qualified workers, junior management, supervisors, foremen and superintendents | 132 | 4 | 1 | 8 | 1 | 85 | 1 | 0 | 13 | 1 | 0 | 0 | 244 |
| Semi-skilled and discretionary decision making | 204 | 3 | 0 | 13 | 4 | 100 | 2 | 1 | 4 | 2 | 0 | 0 | 327 |
| Unskuilled and defined decision making | 243 | 3 | 0 | 3 | 6 | 194 |  | 1 |  | 1 | 0 | 0 | 444 |
| TOTAL PERMANENT | 676 | 11 | 1 | 31 | 12 | 444 | 3 | 2 | 23 | 4 | 0 | 0 | 1191 |
| Temporary employees | 14 | 0 | 0 | 0 | 0 | 1 |  |  |  | 0 | 0 | 0 | 15 |
| GRAND TOTAL | 690 | 11 | 1 | 31 | 12 | 145 | 3 | 2 | 23 | 4 | 0 | 0 | 1206 |

MUNICIPAL POLICIES, PLANS, BYLAWS & STRATEGIES

| NAME | STATUS | ADOPTION DATE |
| --- | --- | --- |
| Acceptance of Grants, sponsorships & gift policy |  | 29/05/2015 |
| Acting Allowances | Under review | 05/05/2011 |
| Alienation of Council Land Policy |  | 24/08/2007 |
| Anti-Fraud and Corruption Policy |  | 07/04/2009 |
| Assets Management Policy |  | 26/05/2015 |
| Attendance of Conferences Workshops and meeting policy |  | 31/07/2000 |
| Audit Committee Charter (2018/2019) |  | 15/11/2018 |
| Bad Debts Write-Off policy |  | 26/05/2017 |
| Bad debts written off policy |  | 31/05/2016 |
| Budget policy |  | 26/05/2017 |
| Business Licensing By-Law | Review | N/A |
| Career Succession Planning policy | Under Review | 24/08/2010 |
| Cash Management and investment Policy |  | 31/05/2016 |
| Customer Care Policy | Reviewed | 29/08/2019 |
| Credit Control & Debt Collection policy & By-Law |  | 26/05/2017 |
| Deposit policy |  | 26/05/2017 |
| Disability policy |  | 09/12/2016 |
| Disposal Policy |  | 29/05/2014 |
| Education, Training and Development Policy |  | 28/05/2019 |
| Employee Assistance/ Wellness | Under Review | 12/20/2010 |
| Employee Exit | Reviewed | 29/08/2017 |
| Employee Performance Management Policy |  | 25/08/2015 |
| Employment Equity Policy |  | 07/12/2011 |
| Expanded public works program policy EPWP |  | 25/11/2014 |
| Financial Assistance for Funerals and Memorial Services to Officials |  | 05/05/2011 |
| Fire & Disaster Management By-Law |  | 28/02/2017 |
| Gender Policy |  | 30/5/2013 |
| HIV/AIDS Workplace Policy |  | 30/05/2011 |
| ICT Policy |  | N/A |
| IDP Process Plan (2019/2020) |  | 29/08/2018 |
| Indigent Household Subsidy policy |  | 26/05/2017 |
| Integrated Development Plan (IDP 2017 – 2021) |  | 26/05/2017 |
| IDP Review (2018/19) |  | 29/05/2018 |
| Integrated Environmental Management Plan | Draft | N/A |
| Integrated Environmental Management Policy |  | 02/12/2015 |
| Integrated Waste Management Plan (IWMP) |  | 09/12/2016 |
| Internal Audit Charter (2018/19) |  | 15/11/2018 |
| Job Evaluation Policy |  | 29/05/2018 |
| Labour Relations |  | 12/20/2010 |
| Language Policy |  | 09/12/2016 |
| Leave policy |  | 28/05/2019 |
| Marketing & Communication policy |  | 26/05/2017 |
| Mayoral bursary Fund |  | 28/03/2014 |
| Mayoral Fund Policy |  | 28/03/2014 |
| Medical Surveillance | Under review | 05/05/2011 |
| Occupational Health & Safety | Reviewed | 29/05/2018 |
| Open Space By-Law |  | 26/05/2017 |
| Operational Manual of Land Alienation Policy |  | 07/04/2009 |
| Outdoor Advertising By-Law | Review | N/A |
| Overtime Management Policy | Reviewed | 27/08/2019 |
| Payroll Policy |  | 29/05/2014 |
| Petty Cash policy |  | 30/05/2013 |
| PMS Framework & Procedure Manual (2017/2018 |  | 26 May 2017 |
| Policy on Civic Funerals and Memorial Services for Councillors |  | 25/08/2015 |
| Policy on Council Houses |  | 09/11/2000 |
| Procedures on Development & Adoption of Policies & By-Laws. |  | 26/05/2017 |
| Property Rates Policy & By-Law |  | 26/05/2017 |
| Public Parks By-Law |  | 26/05/2017 |
| Public participation Policy |  | 23/02/2016 |
| Records Management Policy |  | 26/08/2014 |
| Recruitment, Selection & Personnel | Reviewed | 29/05/2019 |
| Renaming of Street and Other Public Places Policy |  | 30/05/2013 |
| Risk Management Framework, Strategy & Policy |  | 28/02/2017 |
| Sexual Harassment Policy |  | 05/05/2011 |
| Spatial Development Framework |  | 26/05/2017 |
| Spatial Planning & Land Use Management By-Law |  | 28/02/2017 |
| Staff Placement Policy |  | 28/08/2018 |
| Staff & Skills Retention |  | 24/08/2010 |
| Standby Allowance policy |  | 27/08/2013 |
| Standing Municipal Instructions on Legal Matters |  | 26/05/2017 |
| Street Trading By-Law | Review | N/A |
| Study Aid Policy | Reviewed | 28/05/2019 |

| NAME | STATUS | ADOPTION DATE |
| --- | --- | --- |
| Subsistence and Travel Policy |  | 29/05/2014 |
| Supply Chain Management Policy |  | 26/05/2015 |
| Tariff Setting Policy & By-Law |  | 26/05/2017 |
| Transport policy |  | 24/07/2002 |
| Vehicle Allowance Policy |  | 29/08/2017 |
| Volunteers Policy and Procedures | Under review | 07/12/2011 |
| Water Services Development Plan (WSDP) |  | 09/12/2016 |
| Youth Development Policy |  | 07/12/2011 |

SWOT ANALYSIS

| STRENGTHS |  |
| --- | --- |
| - Collective Leadership - Stable political leadership - Sound employer and employee relations - Communication (Corporate) - Economic Infrastructure of Municipality – Dams, Rivers and Natural Beauty - Good Governance systems in place - Senior Management positions have been filled with skilled personnel - Public Private Partnerships in place - Highest allocation of MIG - Permanent administrative leadership - Attractive Tourism, farming and manufacturing industry - Agricultural land | - Gateway that connects countries and provinces - Strong Mining Sector - Municipal structures in place and functional – Council, Subcommittees, AC, RMC, etc… - Adequate public engagements - Performance Management System (Policy Framework, SDBIP, PA, PDP & PC) - Integrated Development Planning (5 Year Plan & Reviews) - Risk Management (Awareness, Prevention & Combating) - MPAC (Oversight & Accountability opportunities) Chief Whip } Political Leadership, Stake- Speaker } holder Engagement and Com- Executive Mayor } munity Involvement; Multi- Party Governance & Decision Making |
| WEAKNESSES |  |
| - Low staff morale - Misplacement of personnel in wrong positions - Non-adherence to the value system Non-adherence to the policy implementation - Unskilled Labour force due to inadequate implementation of the WSP - Inability to resolve long outstanding labour and litigations disputes - Poor revenue collection - Consequence management not in place - Overloaded and aged infrastructure - High staff turnover in critical posts - Lack of review and enforcement of by-laws - Dependency of government grants - Poor planning and planning tools - Poor communication processes and systems - Poor Financial Management - Skills shortages in critical positions - None compliance to policies, acts and legislation - Inability to provide basic services to communities - Failure to update asset register and valuation roll - Ineffective use of resources - High Levels of fraud, corruption and maladministration | - Poor municipal branding/marketing - Delay in payments of service providers - Water crisis in the Municipality - Illegal connection on water and electricity - No integrity of systems, SCM practices - Ill Discipline - High Vacancy rate - Lack of resources - Budget constraint - Outsourcing of critical departmental functions - Lack of available land for residential purposes - High level grant dependency - Appraisals, Cascading PMS to lower levels - Poor implementation of the plan and non-review of Sector Plans - Communication Policy review - Non-functioning of Committees - Poor functioning of Portfolio Committees 8 & 10 - Non-compliance with Municipal Calendar - Lack of accountability - Independence of existence - Undermine basic principles of corporate governance - Political-Administrative Interface compromised |

| OPPORTUNITIES |  |  |
| --- | --- | --- |
| - Big population (growth potential) - PPP availability in the mining, agriculture and motor industry - Use of technology to improve service delivery - Location of mining, tourism and Agricultural industries to the Municipality - Land availability for Industrialization - Maximise revenue streams - Attract investment and Tourists in the Municipality - Infrastructure expanding - Land expropriation/acquisition - Mining and Industrial development |  | - Turn around possible under administration phase - Forensic clean out - Revenue enhancement initiatives - Outsource specific functions - Enhancement of revenue - Recruiting a diverse work force - Migration and urban-led growth drive the local economy - Alternative building technology - Geographic location - National and Provincial Support with Capacity - Development and financial allocation |
| THREATS |  |  |
| - Poor Economic climate and outlook - Non-payment of services by communities and businesses - Unrests and protests by Communities - Mushrooming of Informal settlements - Vandalism of Municipal Assets - High Levels of unemployment - High Levels of Crime - Environmental pollution - Poor perception of Municipality - National political direction - Land instability threat - Public image and reputation - Unfunded and inadequate budget - Fleet - Aged infrastructure | - Loss of revenue - Low personnel morale - Litigation - Service providers are not paid within 30 days - Lack of bulk infrastructure - Long turnaround time in procurement - Informal Settlements - Instability - AG Opinion - Dysfunctional Intergovernmental Relation Structures - District Mayors Forum, Municipal Managers Forum - Alignment of Planning and Implementation Programme between District and Municipalities, as well as Spheres of Government |  |

ORGANISATIONAL RISKS  2020/21

| Directorate | Risk ref as per IDP | KPA | Strategic Objective | KPI | Risk description | Risk category | Root Cause | Consequence | Impact | Likelihood | Inherent risk | Existing controls | Control Adequacy (%) | Residual risk | Treatment plan/ mitigation strategy | Unit Measure | Due date | Freq. of Reporting | Action owner | Risk Owner | Risk Management / Security/Inspection/ Quality & Compliance |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 1st | 2nd |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | line of assurance |  |  |
| ITS | Strategic Objective 4.4.1 | Basic Service Delivery and Infrastructure | Comply to prescribed water quality standards | Compliance to SANS 241 | Failure to comply to all requirements of SANS 241 | Service delivery | 1. Non payment of service providers 2. Delay in procuring material 3. Insufficient budget 4. Non Implementation of the Water Safety Plan and the Maintenance plan | 1. Poor quality of water 2.Contravention with the Constitutional provisions 3.Community unrest 4.Business loss 5.Non Compliance with SANS 241 6. Litigation 7. Water born-diseases 8. Withdrawal of the licence | 5 | 5 | 25 | 1. Audit of per-formance of the water treatment works 2. Finalised the recruitment of the chief engineer for water 3. Sampling and analysis by an independent SANAS accredited Lab 4. Agreed program with the dept. Social & Community Services for vegetation management 5. Service Provider appointed to assist with urgent main-tenance 6.Water Safety Plan | 0 | 25 | 1. Essential services payment prioritised - Water Service Providers (DWS & Maintenance Contractors ) 2. SCM to introduce inventory re-order levels to avoid running out of stock 3. Source additional budget 4. Develop the risk abatement plan 5. Review of the water safety and maintenance plan 19/20 / Action plan 6. Implementation of the 19/20 water safety and maintenance plan | 1. Contractor Statements 2. System enhancement clip/report 3. Motivation for additional funding submitted to top management / Adjustment Budget 4.Risk Abatement plan/council resolution. 5. Reviewed plans and Action plan 6. Monthly Progress Report | 1. Within 30 days of invoice 2. 30 August 2019 3. Nov - Jan 2020 | Monthly | Director ITS | Municipal Manager | Risk Management |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 4. 15 August 2019 5. 15 August 2019 6. As per Action Plan |  |  |  |  |
| ITS | Strategic Objective 3.5.2 | Basic service delivery and infrastructure | Improve the effluent quality compliance | No of wastewater treatment works complying 90% against the applicable water quality standards |  |  | 1. Lack of rehabilitation budget for Mothutlung & Letlhabile 2. Mothotlung and Letlhaile Waste Water Plants Vandalised | 1.Non-compliance to SANS241 2.Risk of litigation by affected communities 3.Contamination to the environment. 4.Withdrawl of water use licence 5.Effluent will be below standards 6. DWS Directives | 5 | 5 | 25 | 1. Audit of performance of all waste water treatment plants. 2.Sampling and analysis by an independent SANAS accredited Lab | 0 | 25 | 1. Solicit funding from alternative sources (MIG, Mines, etc.) 2. Put up fencing at Letlhabile sewer plant to unlock the insurance cover for restoration of the vandalised plant. 3. Maintain sewer network pump stations | 1. Adjusted Budget / Letter of approval for funding 2. Report accompanied by pictures 3. Maintenance Progress Report | 1. Oct. - Jan. 2020 2. December 2019 3. Monthly Progress Report | Monthly | Director: ITS | Municipal Manager | Risk Management |

| Directorate | Risk ref as per IDP | KPA | Strategic Objective | KPI | Risk description | Risk category | Root Cause | Consequence | Impact | Likelihood | Inherent risk | Existing controls | Control Adequacy (%) | Residual risk | Treatment plan/ mitigation strategy | Unit Measure | Due date |  | Freq. of Reporting | Action owner | Risk Owner | Risk Manage-ment / Security /nspection/ Quality & Compliance |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 1st | 2nd |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | line of assurance |  |  |
| BTO | Strategic Objective 6.1.15 | Financial Viability | Improved Financial Viability and Audit Outcomes | Improve the opinion to Qualified Audit opinion | Lack of credible annual financial statements and supporting documents | Reputation | 1. Lack of proper planning towards preparation of annual AFS 2.No directorate SOP and lack of commitment toward Implementation of internal controls by directorates 3. Lack of commitment towards implementation of AG recommendations. 4. Deliberate circumventing of controls 5. Impunity of transgressors | 1. Reputational Damage 2. Low internal, external stakeholder and investor confidence. 3. Poor Govern-ance 4. Adverse audit opinion | 5 | 5 | 25 | 1. Service Providers appointed 2. Financial management and reporting positions filled 3. PAAP 4. Prior year financials | 10 | 23 | 1. Compile a register key documents (POE) required for submission of AFS according to directorates and track progress. 2. Consolidate the Audit Action Plan with Key documents list. 3. Compile a register of recommendation of the AG for two financial years 4. Compile an audit file from the start of January 5. Implement AG recommendations 6. Implement Internal Audit recommendation 7. Implement Standard Operating Procedures 8. Implement Monthly recons 9. Produce Interim Financial Statement through implementation of the preparation plan for AFS | 1. Steering committees minutes. 2. Register of Key documents and progress thereof. 3. Register of AG recommendations and progress thereof. 4. Audit file submitted to IA for verification - assurance by IA - submission register | 1. 30 August 2019, monthly 2. 30 August 2019, monthly 3. 30 August 2019 4. 30 January 2020 | 10 October 2019 15 January 2020 10 April 2020 10 July 2020 |  | All Directorates Manager: Financial Reporting | Municipal Manager | Risk Management |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 5. Progress report on implementation of the AG recommendations 6. Progress report 7. Compliance report to SOPs 8. Monthly recons 9. Interim AFS | 5. 30 August 2019 6. 30 August 2019 7. 30 August 2019 8. 30 August 2019 9. 30 September 2019 |  |  |  |  |  |

| Directorate | Risk ref as per IDP | Key Performance Area | Strategic Objective | KPI | Risk description | Risk category | Root Cause | Consequence | Impact | Likelihood | Inherent risk | Existing controls | Control Adequacy (%) | Residual risk | Treatment plan/mitigation\ strategy | Unit Measure | Due date | Freq. of Reporting | Action owner | Risk Owner | Risk Management / Security/Inspection/ Quality & Compliance |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 1st | 2nd |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | line of assurance |  |  |
| ITS | Strategic Objective 3.4.2. | Basic service delivery and infrastructure | Monitoring of unaccounted water supply | % reduction of water loss | Increase of water distribution losses | Service delivery | 1.Lack of funding 2.Community resistance 3. Non implementation of the water loss strategy | 1.Increase unaccounted for water 2.High water demand 2.community unrest 3.Business loss | 5 | 5 | 25 | 1. Bulk line audit conducted 2. Appointed chief engineer for water 3.Water Reduction strategy in place 4.Water safety Plan in place | 0 | 25 | 1. Source additional funding 2. Implement the water loss strategy | 1. Adjustment budget 2. Progress report on imple- mentation of the water loss strategy | 1. 31 January 2020 2. August 2019, monthly | Monthly | Director: ITS | Municipal Manager | Risk Management |
| BTO | Strategic Objective 6.1.15 | Financial Viability | Improved Financial Viability and Audit Outcomes | Improve the opinion to Qualified Audit opinion | Lack of credible annual financial statements and supporting documents | Reputation | 1. Lack of proper planning towards preparation of annual AFS 2.No directorate SOP and lack of commitment toward Implementation of internal controls by directorates 3. Lack of commitment towards implementation of AG recommendations. 4. Deliberate circumventing of controls 5. Impunity of transgressors | 1. Reputational Damage 2. Low internal, external stakeholder and investor confidence. 3. Poor Governance 4. Adverse audit opinion | 5 | 5 | 25 | 1. Service Providers appointed 2. Financial management and reporting positions filled 3. PAAP 4. Prior year financials | 10 | 23 | 1. Compile a register key documents (POE) required for submission of AFS according to directorates and track progress. 2. Consolidate the Audit Action Plan with Key documents list. 3. Compile a register of recommendation of the AG for two financial years 4. Compile an audit file from the start of January 5. Implement AG recommendations 6. Implement Internal Audit recommendation 7. Implement Standard Operating Procedures 8. Implement Monthly recons 9. Produce Interim Financial Statement through implementation of the preparation plan for AFS | 1. Steering committees minutes. 2. Register of Key documents and progress thereof. 3. Register of AG recommendations & progress thereof. 4. Audit file submitted to IA for verification - assurance by IA - submission register | 1. 30 August 2019, monthly 2. 30 August 2019, monthly 3. 30 August 2019 4. 30 January 2020 | 10 October 2019; 15 January 2020 10 April 2020; 10 July 2020 | All Directorates Manager: Financial Reporting | Municipal Manager | Risk Management |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 5. Progress report on implementation of the AG recommendations 6. Progress report 7. Compliance report to SOPs 8. Monthly recons 9. Interim AFS | 5. 30 August 2019 6. 30 August 2019 7. 30 August 2019 8. 30 August 2019 9. 30 September 2019 |  |  |  |  |

| Directorate | Risk ref as per IDP |  | KPA | Strategic Objective | KPI | Risk description | Risk category | Root Cause | Consequence | Impact | Likelihood | Inherent risk | Existing controls | Control Adequacy | Residual risk | Treatment plan/ Mitigation strategy | Unit Measure | Due date | Frequency of Reporting | Action owner | Risk Owner | Risk Man. Security/ Inspection/Quality & Compliance |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 1st | 2nd |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | line of assurance |  |  |
| BTO | Strategic Objective 6.1.12 | Financial Viability |  | Improved Financial Viability & Audit Outcomes | Annual Financial Statements sub-mitted to AGSA by 31 Aug 2020 | There may be non or late sub-mission of financial statements | Compliance \ Regulatory | 1. Lack of proper planning towards AFS preparation. 2. Lack internal controls for day to day transactions and processes affecting submission of AFS. 3. Delayed commitment to preparation of AFS. | 1. Late sub-mission of AFS 2. Non-Compliance with Section 126 of MFMA. 3. Qualification of AFS by AG. | 5 | 5 | 25 | Weekly steering committee which is chaired by the Accounting Officer and monitored by the Chief financial officer. | 15 | 21 | 1. By weekly AFS steering committee meetings 2. Implementation of the AFS preparation plan 3. Categorize Action Plan into Directorates and progress should be included in their monthly reports by the respective director (Serve at Top Management). | 1. Minutes of PAAP and Top Man.. 2. Progress report on AFS prep. Plan | 10 October 2019; 15 January 2020 10 April 2020; 10 July 2020 | 1Quarterly | Manager: Financial reporting | CFO | Risk Management |
| BTO | Strategic Objective 6.1.4 | Financial Viability |  | Improved Financial Viability and Audit Outcomes | % of total operating budget revenue raised by 30 June 2020 | Unfunded Budget | Financial | 1. Incorrect budget projection from Service Charges forecast. 2. Incomplete meter reading (due to faulty meters and restriction in some areas) 3. Incomplete billing information (properties water and electricity, refuse and sanitation connection points) 4.Tariffs linked to incorrect category consumer account. 5. Poor maintenance and non-replacement of absolute meters by ITS 6. Denial of access to meters for meter reading purpose by community members |  | 5 | 5 | 25 | 1. Submission of faulty meters report 2. Monthly Revenue report 3. Billing 4. Valuation roll | 15 | 21 | 1. Monthly Service Charges Reconciliations (Tariff report, Property, Account charges) 2. Monthly Service Charges Reconciliations (Service Charges vs GL) 3. Timeous replacement of faulty meters by Technical Department 4. Report on incidences of service interruptions and restrictions by community meter to be included in the monthly report 5. Develop Financial Recovery Plan 6. Develop Revenue Enhance Plan 7. Implement both the financial recovery and revenue enhancement plan 8. Conduct the Cost of Supply Study | 1. Monthly Service Charges reconciliations 2. Signed/emailed (Revenue and Technical) Faulty Meters report. 3.Mothly Revenue Report , BTO monthly report and Council Resolution. | 10 October 2019; 15 January 2020 10 April 2020; 10 July 2020 | 1-4 30 August 2019, monthly | CFO | Municipal Manager | Risk Management |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 4.Report 5. Financial Recovery Plan 6. Revenue Enhancement Plan 7. Progress Report 8. Progress Report |  |  |  |  |  |

| Directorate | Risk ref as per IDP | KPA | Strategic Objective | KPI | Risk description | Risk category | Root Cause | Consequence | Impact | Likelihood | Inherent risk | Existing controls | Control Adequacy | Residual risk | Treatment plan/ Mitigation strategy | Unit Measure | Due date | Freq. of Reporting | Action owner | Risk Owner | Risk Man. Security/ Inspection/Quality & Compliance |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 1st | 2nd |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | line of assurance |  |  |
| ITS | Strategic objective 3.2.1 | Basic service delivery & infrastructure | Monitoring energy losses | % unaccounted for electricity by 30 June 2020 | Increase in electricity losses | Service delivery | 1.Lack of budget; 2. illegal connections 3.meter tampering 4. billing errors; | 1.Increase in electricity losses 2. low revenue collection | 5 | 5 | 25 | 1.Electricity Master plan. 2.Refubishment Plan 3.Maintenace Plan | 20 | 20 | 1.Appointment of a service provider 2.Installation of electricity split meters | 1.Appointment letter 2.Installation report. | 1.30 November 2019 2.30 March 2020 | Monthly | Director: ITS | Municipal Manager | Risk Management |
|  |  |  | Provision of stable electricity supply | Refurbishment of De Kroon substation; | Inability to provide stable electricity supply. |  | Lack of budget | Loss of revenue; decline to the Brits economy. | 5 | 5 | 25 | 1.Implementation of the 2.Maintenance plan | 20 | 20 | Implement the maintenance plan | maintenance report | Monthly ( continuous) | Monthly | Director: ITS | Municipal Manager | Risk Management |
|  |  |  | Secure infrastructure grants ( INEP,MIG, PIG) | % of spending on infrastructure grants allocated | The Municipal Infrastructure Grant allocation might be stopped/withdrawn. |  | 1. Poor performance of contractors 2.Delay on SCM process 3.Community unrests 4. Non compliance to grants conditions | 1.Low spending on grants 2. Reduction/ Loss of grants 3. Non compliance to grants conditions | 5 | 5 | 25 | 1.Implementation plan 2.Procurement plan | 20 | 20 | 1 .Weekly follow-up meeting between ITS & SCM on procurement plans and speedily appointment of contractors 2. Implementation of the MIG project plan 3.Monthly projects monitoring meetings with service providers 4. Appointment of all service providers | 1.Monthly reports with intervention/ minutes of meetings. 2. Monthly progress report with progress on site and expenditure levels 3.Monthly reports with intervention/ minutes of meetings. 4. Appointment letters | 1- 3 . 30 August 30 September 2019 | Monthly ( continuous) | Director: ITS | Municipal Manager | Risk Management |

| Directorate | Risk ref as per IDP | KPA | Strategic Objective |  | KPI | Risk description | Risk category | Root Cause | Consequence | Impact | Likelihood | Inherent risk | Existing controls | Control Adequacy | Residual risk | Treatment plan/ Mitigation strategy | Unit Measure | Due date | Frequency of Reporting | Action owner | Risk Owner |  | Risk Man.Security/ Inspection/Qua lity & Compliance |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 1st | 2nd |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | line of assurance |  |  |  |
| CSS | Strategic Objective 1.2.6 | Municipal Transformation and Institutional Development | Improved Effectiveness and Efficiency of Municipal Administration | Number of critical prioritised posts filled by 30 June 2020 |  | Failure to fill the critical prioritised posts by the targeted date | Human Resources | Delay by council to conclude recruitment process | Negative Audit opinion No accountability Limited capacity | 5 | 5 | 25 | 1.Regulations on appointment of senior managers 2.Administrative requirement have been met . | 20 | 20 | Director to write a report to council on appointment of senior managers . | Report to council | 31 December 2019 | Quarterly | Director: CSS |  | Municipal Manager | Risk Management |
| SPME | Strategic Objective 7.2.1 | Good Governance and Public Participation | Improved implementation of fraud prevention plans | % of implemented fraud prevention plans by 30 June 2020 |  | Increase in fraud activities | Fraud and corruption | 1.Lack of buy-in management 2.Lack of continuous review 3.Lack of monitoring 4.Outdated anti-corruption policy 5.Non implementation of fraud plans | 1.Non compliance . 2.Negative audit opinion. 3.Poor governance . 4. Embezzlement of public funds | 5 | 5 | 25 | Anti-Corruption policy - 2009 | 20 | 20 | 1.Incorporating fraud and corruption in senior management performance agreements. 2.Establish integrity management committee . 3.Report incidents of fraud and corruption to Commission of integrity 4. Implement the 19/20 ethics and fraud management plans | 1Reviewed performance agreement 2019/2020 2.Appointment letters 3.Quartely report 4. Progress Report | 1. 30. September 2019 2. 30. September 2019 3. 31, March 2020 4. 30 September 2019 | Quarterly | Deputy Director: SPME |  | Municipal Manager | Risk Management |

| Directorate | Risk ref as per IDP | KPA | Strategic Objective | KPI | Risk description | Risk category | Root Cause | Consequence | Impact | Likelihood | Inherent risk | Existing controls | Control Adequacy | Residual risk | Treatment plan/ Mitigation strategy | Unit Measure | Due date | Frequency of Reporting | Action owner | Risk Owner | Risk Man. Security/ Inspection/Quality & Compliance |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 1st | 2nd |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | line of assurance |  |  |
| PSFFM | Strategic Objective 4.1.4 | Improve provision of safe environment | Reduction in By-law contraventions | No. of By-Laws enforcement programmes held by 30 June 2020 | Failure to implement council bylaws | Compliance \ Regulatory | 1. Insufficient budget 2. Reviewing of By Laws 3.Interdepency on other Departments 4. No peace officers | 1.Creating a health Hazard 2.AG finding 3. Loss on revenue 4. Chaos /lawlessness | 5 | 5 | 25 | 1.Monthly Meetings with SAPS 2.1 x Senior Law Enforcement Officer Appointed 3.Programs form Fire and Disaster Management with relevant Stakeholders | 20 | 20 | 1. Appointment of Law Enforcement Inspectors 2. Programs planned within allocated budget 3.Establisment of an Inter Departmental By Law Enforcement Committee | 1. Appointment Letters 2.Quartely Program Rosters By - Law Enforcement 3.Invitation, Minutes and Attendance Register | 1. October 2019 2. Quarterly 3. February 2020 | 30 September 2019 31 December 2019 31 March 2020 30 June 2020 | Director PSFFM | Municipal Manager | Risk Management |
| BTO | Strategic Objective 6.1.3 | Financial Viability | Improved Financial Viability and Audit Outcomes | % of total operating Budget expenditure spent by 30 June 2020 | There might be a lack of Cash to spend | Financial | 1. Weak internal control on (budget control & standard operating procedures). 2. Weak internal control on (expenditure management and standard operating procedures). 3. Poor planning and implementation of Procurement Plans 4. Inadequate utilisation of Creditors module on the Financial Management System 5. Failure to collect budgeted revenue | 1. Unauthorised expenditure. 2. Qualification of AFS. 3. Hampering of service delivery. 4. Incurring of fruitless and wasteful expenditure 5. Duplicate payments to Creditors | 5 | 5 | 25 | 1. Manually utilisation of creditors reconciliation template 2. Utilisation of cheque requisition with delegated approvals 3. Utilisation of Creditors module on Trade Creditors | 20 | 20 | 1. Centralisation of points of submission of Invoices ( Ex-penditure Unit). 2. Training of Expenditure personnel on the Creditors module. 3. Financial System budget expenditure authorization be limited to the CFO and budget manager 4. Resuscitate Cost containment committee | 1. Memo by the CFO to all staff ( Centralisa-tion) 2. Training Attendance Certificates 3. Signed override authorisation form and system print out 4. appointment letters and sitting schedule | 1. 30 August 2019, monthly 2. 30 September 2019 | 10 October 2019 ( Memo and Training) 10 October 2019 15 January 2020 | CFO | Municipal Manager | Risk Management |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 3. 30 August 2019 4. 30 August 2019 | 10 April 2020 10 July 2020 |  |  |  |

| Directorate | Risk ref as per IDP | KPA | Strategic Objective | KPI |  | Risk description |  | Risk category |  | Root Cause | Consequence | Impact | Likelihood | Inherent risk | Existing controls | Control Adequacy | Residual risk | Treatment plan/ Mitigation strategy | Unit Measure | Due date | Frequency of Reporting | Action owner | Risk Owner |  | Risk Man.Security/ Inspection/Qua lity & Compliance |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 1st | 2nd |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | line of assurance |  |  |  |
| BTO 6 | Strategic Objective 6.1.6 | Financial Viability | Improved Financial Viability and Audit Outcomes | % of tenders completed within the valid period (90 days from date of closure of advert) by 30 June | There might be delays on sitting of Bid Committee meetings |  | Compliance \ Regulatory |  | 1. No Capex and Opex procurement annual plan with committees setting schedule. 2. Lack/ineffectiveness of communication with appointed committee members. 3. Unavailability of committee members. 4. Late submission from user Departments |  | 1. Irregular Expenditure 2. non-compliance with the validity period/ time frame | 5 | 5 | 25 | 1. Scheduled Bid Committee meetings 2. Approved procurement plan | 20 | 20 | 1. Compile Capex and Opex procurement plan with Committee setting schedule. 2. Effective communication with appointed committee members | 1. Capex and Opex procurement plan with setting schedule. 2. Appointment letters of committee members | 10 October 2019 15 January 2020 10 April 2020 10 July 2020 | Quarterly | CFO |  | Municipal Manager | Risk Management |

| COMMENTS FROM THE AUDITOR-GENERAL’S REPORT |  |
| --- | --- |

Report of the auditor-general to the North West provincial legislature

and the council on the Madibeng Local Municipality

STRATEGY PHASE

KPA 2 : GOOD GOVERNAnce

INTEGRATED DEVELOPMENT PLANNING PUBLIC PARTICIPATION

IDP & Budget Process

The requirements of Sections 25(1),  28(1) and 34 of the Municipal Systems Act, 32 of 2000, as set out below, guide municipalities in terms of formulating IDP’s:

Section 25(1) that “Each municipal council must, within a prescribed period after the start of its elected term, adopt a single and inclusive strategic development plan for the development of the municipality”; and

Section 28(1) states further that “each municipal council must, within a prescribed period after the start of its elected term, adopt a process that set out in writing to guide the planning, drafting, adoption and review of its integrated plan.

section 34 reads as follows:   “A municipal council

(a) must review its integrated development plan –

(i) annually in accordance with an assessment of its performance measurements in terms of section 41; and

(ii) to the extent that changing circumstances so demand; and

(b) may amend its integrated development plan in accordance with a prescribed process”

Background

The 5 Year IDP (2017/21), being the 4th generation of the Municipal IDPs, was adopted by Council on 26 May 2017 as per resolution A.0157. In accordance with Section 34  the IDP 5 Year plan was thereafter reviewed as follows:

2017/18 IDP Review formed part of the 5 Year IDP that was adopted on 26 May 2017;

2018/19 IDP Review was  adopted on 29 May 2018.

2019/20 IDP Review was adopted on 28 May 2019

2020/21 IDP Review, being the last review of the current 5 Year Plan, to be adopted during May 2020

IDP Process Plan

The IDP Process Plan for the 2020/21 IDP Review was adopted by Council on 27 August 2019 as per resolution Admin.0017.

Purpose of the IDP Public Participation Process

This Process Plan, amongst others, requires that the municipality embarks on the process of ward level public participation to review the ward priority needs and prioritized projects as indicated in the adopted document. Madibeng is addressing its public participation by hosting individual ward level meetings in all wards within its jurisdiction.

The Process of Ward Level Public Participation

According to the IDP and Budget Process Plan the IDP Ward Public Participation Process successfully took place during October 2019.

The Municipality complied to the prescribed legislative requirements, whereby 2 weeks prior notice to the commencement date of the Ward Level Public Participation Process were given to the communities and stakeholders

This was done as follows:

A Notice of the scheduled Ward Level Public Participation Meetings appeared in the local Naledi Newspaper on 30 September 2019.  Notices, in the form of flyers, were distributed by the respective Ward Councillors and loudhailing was done by the Office of the Speaker, whilst broadcasting was done by Radio stations Lethlabile and Moitswading respectively.

Constitution of Task Teams

Ten task teams, comprising of MMCs, Directors, Managers and other officials, were nominated to attend these meetings.

Outcome of IDP Ward Level Public Participation Process

The success rate of this exercise was 83% and the ward needs were prioritized as follows:

PRIORITIZED WARD NEEDS AND PROJECTS

| WARD 1 |  |  |  | WARD 3 |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| NEEDS | PROJECTS | AREAS |  | NEEDS | PROJECTS | AREAS |
| 1. Water & Sanitation | - Rehabilitation of boreholes 1.2. Maintenance of boreholes (Plan) 1.3. Bulk Water 1.4. Water Borne Toilets 1.5. VIP Toilets | Legonyane, Sephai, Fafung, Rasai, Klipvoor, Vaalbosch, Rooival, Mmasebolana & Kwarriekraal All Areas All areas Legonyane, Fafung, Rasai, Klipvoor, Vaalbosch, Rooival & Mmasebolana As in point 1.1. above |  | 1. Water & Sanitation | 1.1. Bulk Supply 1.2. Purification and Completion of Borehole Project, Blue drop Madidi Purification Plant (Letter of approval from (Munici- pality) 1.3. Improved Water Quality 1.4. VIP Flush Toilets 1.5. Sewer System | Infrastructure where it is non-existent and extension of pipeline Madidi & Lekgema |
| 2. Roads & Storm water | 2.1. Upgrading of tarred roads Roads 2.2. Gravelling/Paving of Internal 2.3. Stormwater drainage 2.4. Upgrading of bridges & culverts 2.5. Road Signs & Fencing | All areas / Rooival, Vaalboschloot, Klipvoor, Kwarriekraal All areas All areas Klipvoorstad, Legonyane & Sephai All areas |  | 2. Social Services | 2.1. 24 Hour Clinic Service 2.2. Sports Facility 2.3. Waste Transfer Station 2.4. Skills Development Centre (ABET) 2.5. Completion of local Park |  |
|  |  |  |  | 3. Roads & Storm water | 3.1. Regravelling of roads 3.2. Construction of pedestrian bridge 3.3. Paving and storm water for internal roads 3.4. Rehabilitation of Provincial roads 3.5. Tarred roads | All Areas Madidi & Lekgema Lekgema & Madidi Madidi & Lekgema |
| 3. Social Services | 3.1. Development of clinic 24 hrs 3.2. Maintenance of all community halls 3.3. Development of Waste Disposal 3.4. Development of community halls 3.5. Development of park | Fafung & Legonyane Rooival, Kwarriekraal |  |  |  |  |
|  |  |  |  | 4. Electricity | 4.1. High Mast Lights 4.2. Provision of electricity 4.3. Energizing and maintenance of post connection 4.4. Electrification project 4.5. Upgrading of transformer | Lekgema B/D Lekgema & Madidi All Areas |
| 4 .Electricity | 4.1. Extension to other areas 4.2. Maintenance of Apollo Lights (energised) 4.3. Additional Apollo Lights 4.4. Post connection | All areas All areas |  |  |  |  |
| 5. Land and Housing | 5.1. PHP Houses 5.2. RDP houses | Fafung, Sephai, Rasai, Legonyane, Masobolane and Rooival |  | 5. Land & Housing | 5.1. Acquisition of Land for Tenants & Formalization Process 5.2. RDP Houses | Lekgema |
| WARD 2 |  |  |  | EXCESS NEEDS |  |  |
| NEEDS | PROJECTS | AREAS |  | 6. LED | 6.1 Car Wash Establishment 6.2. Tourism Development 6.3. Business Centre | 6.4. Irrigation System for Crop \ Farming 6.5 Poverty Relief Programme |
| 1. Water & Sanitation | 1.1. Water Supply 1.2. VIP Toilets | Jericho All ward |  |  |  |  |
| 2. Roads | 2.1. Tarred Roads | Jericho to Mmupudung (13 kms) Jericho to Rashoop |  | Roads & SW | 3.6. Speed humps – Madidi Primary School, Mmamonwana Primary School & KB Salon |  |
|  |  |  |  | Social Services | 2.6. Women Empowerment 2.7. Park in Sections – B/K 2.8. Gymnasium 2.9. Technical High School | 2.10. Drug Rehab Centre 2.11. Patrollers 2.12. After Care |
| 3.Electricity | 3.1. High Mast Lights 3.2. Extensions 3.3. Street Lights | All ward |  |  |  |  |
| 4. Housing | 4.1. Rural Housing | All ward |  |  |  |  |
| 5. LED | 5.1. Tourism 5.2. Arts & Culture | All ward |  | WARD 4 |  |  |
|  |  |  |  | NEEDS | PROJECTS | AREAS |
| EXCESS NEEDS |  |  |  | 1. Water & Sanitation | 1.1 Bulk Water 1.2 Sanitation & Sewerage 1.3. VIP Toilets | Bapokeng, Old Stand, Bataung, Tshamahantshe, Doornkop and Ikageng |
| 6. Social Services | 6.1. Renovation of Preschools & Schools 6.2. Extension of Clinic | 6.3. 24 hours working Clinic 6.4. Mobile Clinic twice a week |  |  |  |  |
| WARD 4 (Cont) |  |  |  | WARD 5 EXCESS NEEDS |  |  |
| NEEDS | PROJECTS | AREAS |  | 6. Electricity | 6.1. High Mast Lights 6.2. Post connection | 6.3. Street Lights 6.4. Upgrading Substation |
| 2. Roads & Storm water | 2.1. Upgrading Internal roads 2.2. Tarred roads & bus routes 2.3 Construction of bridges 2.4. Upgrading of Provincial road | Road Z606 from KL to Madinyane and road Z608 from garage to Mahau All Areas as above |  |  |  |  |
|  |  |  |  | Social Services | 3.6. Fencing of cemeteries 3.7. Schools-Technical College, Middle & High - Maboloka |  |
| 3. Social Services | 3.1. Clinics & equipment & staff 3.2. Police Station 3.3. Fencing of cemetery 3.4. Disability Centre 3.5. Sports facilities & Insurance Fund for repairs of Multi- purpose Centre |  |  | WARD 6 |  |  |
|  |  |  |  | NEEDS | PROJECTS | AREAS |
|  |  |  |  | 1. Water & Sanitation | 1.1. Water connections 1.2. Sewerage |  |
|  |  |  |  | 2. Roads & Storm water | 2.1. Construction of Tarred road from K:L to Checkers 2.2. Bridge for school children |  |
| 4. LED | 4.1. Poverty Relieve Programs 4.2 Skills Development Centre 4.3. SMMEs/Cooperatives 4.4. Agriculture 4.5. Culture Village | All Areas as above |  |  |  |  |
|  |  |  |  | 3. Social Services | 3.1. 24h Clinic 3.2. Police Station 3.3. Multi Purpose Centre 3.4. Schools (Technical & Agricultural) 3.5. Fencing of Cemetery | Maboloka |
| 5. Land & Housing | 5.1. PHP and RDP 5.2. PHP funds of housing | All Areas as above |  |  |  |  |
|  |  |  |  | 4. Electricity | 4.1 High Mast Lights 4.2. Extension at Thambo Sec 3 | Maboloka |
| EXCESS NEEDS |  |  |  |  |  |  |
| 6. Electricity | 6.1 Substation 6.2 Maintenance and additional High Mast Lights |  |  | 5. Housing | 5.1 PHP Housing | Maboloka |
|  |  |  |  | EXCESS NEEDS |  |  |
|  |  |  |  | Social Services | 3.6. Waste Bins |  |
| WARD 5 |  |  |  |  |  |  |
| NEEDS | PROJECTS | AREAS |  | WARD 7 |  |  |
| 1. Roads & Storm water | 1.1. Upgrading of gravel & internal roads 1.2. Tarring of Internal Bus Roads | All bus and taxi roads All streets |  | NEEDS | PROJECTS | AREAS |
|  |  |  |  | 1. Land & Housing | 1.1. Low Cost Housing 1.2. Affordable Houses 1.3. Acquisition of Title Deeds 1.4. RDP Houses 1.5.Distribution of Land | Majakaneng |
| 2. Water & Sanitation | 2.1. Bulk Water 2.2. Sewerage & Sanitation | Maboloka |  |  |  |  |
| 3. Social Services | 3.1. Clinic 3.2. Police Station 3.3. Multipurpose Centre 3.4. Sports Centre 3.5. Old Age Home & Orphanage | Bafokeng & Lethabong |  | 2. Water & Sanitation | 2.1. Yard Connections 2.2. Purified water | Some area in all sections |
|  |  |  |  | 3. Roads & Storm water | 3.1 Stormwater drainage 3.2 Internal road paving and backfilling 3.3 Humps in all tar roads 3.4 Paving of Sidewalks | Majakaneng |
| 4. Land & Housing | 4.1. Low Cost Housing & RDP Houses 4.2. PHP Houses 4.3. Constructions | All Sections 1, 2, 3 & 4 Bafokeng, Lethabong & Maboloka |  |  |  |  |
|  |  |  |  | 4. Electricity | 4.1. Yard connections 4.2. Indigent registrations |  |
| 5. LED | 5.1. Agriculture 5.2. SMME & Business Centre | Lethabong Maboloka |  | 5. LED | 5.1 Fet College 5.2. Hawkers Stalls 5.3. Training of SMME’s 5.4. Mini Industry for Manufacturing 5.5. Majakaneng Hiking Trails |  |

| WARD 7 EXCESS NEEDS |  |  |  | WARD 9 (Cont) |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| 6. Social Services | 6.1. Extension of Clinic 24 hours 6.2 Police Station (Satellite) 6.3. Multi Purpose Centre | 6.4. Community crèche 6.5. Development of New Cemetery 6.6. Waste Bins |  | NEEDS | PROJECTS | AREAS |
|  |  |  |  | 2. Water & Sanitation | 2.1 Water Purification Plant 2.2. Boreholes 2.3. Water pipe supply 2.4. Permanent Toilets | Block B, C Block H Block B, C Block B, C, and part of Block H |
| WARD 8 |  |  |  | 3. Land & Housing | 3.1. Formalization 3.2. 5000 RDP Houses 3.3. 3000 PHP Houses 3.4. Affordable Houses 3.5. 2500 vacant stands | Next to the mall Block B, C, and part of Block H |
| NEEDS | PROJECTS | AREAS |  |  |  |  |
| 1. Water & Sanitation | 1.1. Water Reticulation 1.2. Yard Connections 1.3 Rehabilitation of Boreholes 1.4. Sewage system & VIP Toilets | All areas |  |  |  |  |
|  |  |  |  | 4. Electricity | 4.1. Extension of House Connections 4.2. Additional 8 High Mast Lights 4.3. Upgrading of Sub-Station | Block B, C and H All Sections Lethlabile Block C |
| 2. Land & Housing | 2.1. Expropriation of Land 2.3 Land Tenure 2.2. RDP houses 2.4 PHP Houses | Ndlovu and Mashimong All areas |  |  |  |  |
|  |  |  |  | 5. Social Services | 5.1. Clinic 24/7 5.2. Primary School 5.3. High School 5.4. Multi-Purpose Community & Crisis Centre 5.5. Sports Facility | Block B, C, and part of Block H Block H Between Blocks B and C Block C |
| 3. Electricity | 3.1. Electrification 3.2. High Mast Lights 3.3. Post connections 3.4. Upgrading of Sub Station | Klipgat C All areas |  |  |  |  |
|  |  |  |  | EXCESS NEEDS |  |  |
|  |  |  |  | Social Services | 5.6. Food Service School (Disabled people and slow learners) 5.7. Rehab/crisis and development centre 5.8. Parks | 5.9.Technical College 5.10. Police Station/Mobile |
| 4. Roads & storm water | 4.1 Tarring of main roads 4.2. Stormwater Roads 4.3. Regravelling of Roads 4.4. Speed Humps 4.5 Tolaone bridge | Pavement of Madibeng Hills Rd, Jakallas to Mashamplane Rd and Msiza to Phasha Rd All areas All areas Klipgat A & Klipgat C Jakkalsdans |  |  |  |  |
|  |  |  |  | 6. LED | 6.1 Gardening . | 6.2. Car Wash |
|  |  |  |  | WARD 10 |  |  |
| 5. Social Services | 5.1 Parks and Cemetery 5.2 Mobile Clinic 5.3 Satellite Police Station 5.4 Library 5.5. Upgrading of Clinic | All areas Klipgat C Klipgat C Klipgat A Klipgat A |  | 1. Water | 1.1. House Connections | Micha-View, Itereleng, Mmotong, Green Side, Magaseng, Phiring, Kgola & Kagisanong |
|  |  |  |  | 2. Electricity | 2.1. House Connections 2.2. Apollo Lights and Energizing | Kagisanong & Rockville \ Kagisanong, Rockville, Micha-View & Itereleng |
| EXCESS NEEDS |  |  |  |  |  |  |
| 6. LED | 6.1. Sports facilities 6.2 Youth projects 6.3 Poverty alleviation projects | 6.4 Job creation 6.5. Tourism and Agricultural projects – Matebeleng Cultural Village to be revamped |  | 3. Roads and Storm water | 3.1. Stormwater 3.2. Speed humps 3.3. Internal Roads | Kgabalatsane Clinic Kgabalatsdane Clinic Rd & all dangerous areas to be identified by Ward Councillor Freedom Roads, Mthimkhulu, Motong, 3x Kagisong, 3x Rockville, Phuthing & Lutheran Church Roads |
| WARD 9 |  |  |  |  |  |  |
| NEEDS | PROJECTS | AREAS |  | 4. Housing | 4.1. RDP & PHP Housing 4.2. Formalization of Rural Areas | Micha View, Rockvuille, Itereleng, Mmotong, Magaseng, Phiring, Phuting, Kgola & Kagisanong Mmotong, Kagisanang & Micha-View |
| 1. Roads & Storm water | - Paving of internal Roads and Side Kerbs 1.2. Expansion of Road 1.3. Speed humps | Block B, C, and part of Block H Letlhabile to Brits Between Letlhabile and Maboloka |  |  |  |  |

| WARD 10 (Cont) |  |  |  | WARD 12 |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| NEEDS | PROJECTS | AREAS |  | NEEDS | PROJECTS | AREAS |
| 5. Social Services | 5.1. Primary School 5.2. 24 hour clinic & Extension of Mobile Clinic 5.3. Library 5.4. Cemetery 5.5. Rec+reation Park | Rockville, Micha-View, Itereleng & Kagisanong Itereleng, Kagisanong, Micha-View, Rockville & Fencing |  | 1. Water | 1.1. Bulk Water 1.2. Replacement of Water meters | All sections All sections |
|  |  |  |  | 2. Roads & Storm water | 2.1 Storm water Drainage 2.2 Upgrading of Internal Roads 2.3 Speed Humps 2.4. Side Walk Paving 2.5 Expansion of Provincial Road | All sections All sections All sections All sections From Letlhabile to Brits |
| EXCESS NEEDS |  |  |  |  |  |  |
| Social Services | 5.6. School Patrol 5.7. Sport Centre facilities (Rockville, Micha-View, Mmotong, Itereleng & Kagisanong) |  |  | 3. Land & Housing | 3.1. Low Cost & PHP Housing 3.2. Development of New Sites 3.3. Title Deeds | All sections |
| WARD 11 |  |  |  | 4. Social & Services | 4.1 Community Parks 4.2 Sports Field 4.3 Multi Purpose Centre 4.4 FET College 4.5 Police Station | Zone 4, 7, 8, Block F Block F Zone 15 Zone 15 Zone 15 |
| NEEDS | PROJECTS | AREAS |  |  |  |  |
| 1. Roads and Storm water | 1.1. Access Roads 1.2. Tarring of Internal Roads 1.3. Internal Roads Stormwater 1.4. Speed Humps 1.5. Street Names | Block Ext. 1& 2 Block Ext. 1& 2 Block Ext. 1& 2 Zone 16 Block B Ext. 1& 2, Blocks G I and Zone 16 |  |  |  |  |
|  |  |  |  | 5. Electricity | 5.1 House Connections 5.2 Additional Apollo Lights 5.3 Solar Geyser | All sections Block F All sections |
| 2. Land and Housing | 2.1. RDP Houses 2.2. Development of sites & vacant stands 2.3. Low Cost Housing 2.4. Affordable Houses | Block G, I and Ext. 2 Zone 16 Block I |  |  |  |  |
|  |  |  |  | EXCESS NEEDS |  |  |
|  |  |  |  | Social & Services | 4.6. Court 4.7. Orphanage |  |
| 3.Social Services | 3.1. Clinic 24/7 3.2. Technical College & Vocational Education and Training Crisis Centre 3.3. Multi Purpose and Crisis Centre 3.4. Upgrading of Sports Centre adding swimming Facilities 3.5. Primary School | Block B Ext 2 Block G (Next to Lethlabile Mall) Zone 16 |  | 6. LED | 6.1 Skills Development 6.2 Agriculture 6.3. Tourism – (Art & Culture, B&B) 6.4. Flea Market | Zone 15, Block F Zone 15 Zone 15 Zone 15 |
|  |  |  |  | WARD 13 |  |  |
|  |  |  |  | NEEDS | PROJECTS | AREAS |
| 4. Electricity | 4.1. Upgrading of substation 4.2. Extension of house connections 4.3. Additional High Mast Lights 4.4. Solar Geysers | Blocks G Block G and I, Zone 16 Block G Ext. 2 Block G All sections |  | 1. Roads & Storm water | 1.1. Tarring/Paving of internal roads 1.2. Speed humps | At Internal Road for Phase 2 |
|  |  |  |  | 2. Land and Housing | 2.1. RDP Houses 2.2. Acquisition of land for Community, Churches and businesses 2.3. Allocation of empty stands 2.4. Formalization of Informal Settlement | Oukasie |
| 5. LED | 5.1. Agriculture site 5.2. Game Reserve 5.3. Flea Market 5.4. Tourism (LED) 5.5. Museum (Art, Culture) |  |  |  |  |  |
|  |  |  |  | 3. Social Services | 3.1. 24hrs Clinic 3.2 Upgrading of Cemeteries 3.3. High School 3.4. Sports Facility 3.5. Old Age and Disability Home | Vuka |
| EXCESS NEEDS |  |  |  |  |  |  |
| Roads & Stormwater | 1.6. Expansion of Provincial Road 1.7. Sidewalks Paving – Block B Ext 1 and 2, Zone 16 and Busi’s Creche |  |  |  |  |  |
|  |  |  |  | 4. LED | 4.1. Agriculture 4.2. Heritage Site 4.3. Youth Employment to maintain storm water drainage 4.4. Market | Oukasie |
| Social Services | 3.6. Police Station 3.7. Fire Station | 3.8. Community Parks with machinery |  |  |  |  |
| LED | 5.6. Carwash |  |  |  |  |  |
| 6 .Water | 6.1. Main pipe from Brits to Letlhabile |  |  |  |  |  |
| WARD 13 (Cont) |  |  |  | WARD 15 (Cont) |  |  |
| NEEDS | PROJECTS | AREAS |  | NEEDS | PROJECTS | AREAS |
| 5. Electricity | 5.1. Expansion of Power Station 5.2. High Mast Lights 5.3. Service point |  |  | 3. LED | 3.1. Skills Development Centre 3.2. Business Empowerment |  |
|  |  |  |  | 4. Social Services | 4.1. Clinic 4.2. Library 4.3. Park | New Stand & Phase 1 and Phase 2 |
| EXCESS NEEDS |  |  |  |  |  |  |
| Social Services | 3.6. Satellite Police Station 3.7. Multipurpose Centre | 3.8. Closing of Canal |  |  |  |  |
|  |  |  |  | 5. Land & Housing | 5.1. Formalization of Rural Areas 5.2. PHP Housing | All Areas |
| 6. Water and Sanitation | 6.1. Upgrading of water Infrastructure 6.2. Upgrading of sewer Infrastructure |  |  |  |  |  |
|  |  |  |  | EXCESS NEEDS |  |  |
|  |  |  |  | 6. Water & Sanitation | 6.1. Household Connections 6.2. Sewage Systems |  |
| WARD 14 |  |  |  |  |  |  |
| NEEDS | PROJECTS | AREAS |  |  |  |  |
| 1. Land & Housing | 1.1. Formalization of Informal Settlements 1.2. Acquisition of Land for Housing 1.3. RDP Houses 1.4. Title Deeds | All Farm areas, Oukasie Ext. 5, Mosholozi, Rashoop & Wonderpark |  | WARD 16 |  |  |
|  |  |  |  | NEEDS | PROJECTS | AREAS |
|  |  |  |  | 1. Water & Sanitation | 1.1. Yard Connection 1.2 Sewerage 1.3. Water Pay Point 1.4. Zoning of water network – other wards | For all households Itsoseng and Hebron (Roma Section) Itsoseng & Hebron (Roma Section) Itsoseng & Hebron (Roma Section) Itsoseng & Hebron (Roma Section) |
| 2. Electricity | 2.1. Farm Reticulation programme 2.2. Apollo Lights 2.3. House connections 2.4. Household electrification | Mosholozi, Rashoop and Wonderpark |  |  |  |  |
|  |  |  |  | 2. Roads & Storm water | 2.1. Speed Humps 2.2.Tarred Internal Roads 2.3.Tarred Road 2.4. Storm Water Drainage 2.5. Paving of Roads | Itsoseng Itsoseng High School; Molefe Road to Phase 4 internal Bridge to Phase 5, Cemetery Road 10 km Bus Route in Itsoseng Thom Eddy & road behind Tlhako A Thamaga Primary School |
| 3. Roads & Stormwater | 3.1. Stormwater drainage 3.2. Internal Roads & Streets Paved | Oukasie Ext. 5, Mosholozi, Rashoop & Wonderpark |  |  |  |  |
| 4. Water & Sanitation | 4.1. Construction of VIP Toilets 4.2 Sewer connection 4.3 House connection 4.4. Water reticulation | Mosholozi, Rashoop, Oukasie Ext. 5, Informal |  |  |  |  |
|  |  |  |  | 3. Electricity | 3.1. House Connections 3.2. High Mast Lights 3.3. Street Lights 3.4. Upgrading of Electricity | Phase 3 Ext, Phase 5 Ext All areas Hlabirwa store, MD Stores, Roman, Phases Ext, Chico Phase 3, Phase 3 Mountain, Phase 3 Ext. Mountain –Itsoseng,1xRoma,1xSophie, Matshipisane Store |
| 5. Social Services | 5.6. Multipurpose centre 5.7 Satellite Police Station 5.8 Library | 5. Social Services |  |  |  |  |
| EXCESS NEEDS |  |  |  |  |  |  |
| 6. LED | 6.1. Agricultural land and farming 6.2. Tourism site | 6.3. Skills development & Training 6.4. Chicken poultry |  |  |  |  |
|  |  |  |  | 4. Land & Housing | 4.1. Title Deeds 4.2. PHP Houses 4.3. Street Names and House No’s. | Itsoseng & Hebron (Roma Section ) Itsoseng & Hebron (Roma Section ) Itsoseng |
| WARD 15 |  |  |  |  |  |  |
| NEEDS | PROJECTS | AREAS |  | 5.Social Services | 5.1. Health Centre (Clinic) 5.2. Multi-Purpose Centre 5.3. Cemetery 5.4. Library 5.5. Sport Grounds | Dineo Crèche / Community Hall at Itsoseng Itsoseng Community Hall Itsoseng Itsoseng Community Hall Phase 4 and Phase 3 Ext |
| 1. Roads & Storm Water | 1.1. Paved Roads 1.2. Storm water drainage | Royal Rd and New Stand, Phase 2 entrance, Lesedi Mabitleng |  |  |  |  |
| 2. Electricity | 2.1. High Mast Lights 2.2. House Connections 2.3. Reconnection/maintenance of lights 2.4. New Street lights | 3 Extra – Rolling Stars Groud, Itsoseng Phase 1 & Moagi Ext. 5 High Mast Lights for maintenance |  |  |  |  |

| WARD 16 EXCESS NEEDS |  |  |  | WARD 18 (Cont) |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Social Services | 5.6. Police Station |  |  | NEEDS | PROJECTS | AREA |
|  |  |  |  | 3. Land and Housing | 3.1. RDP Houses 1000 3.2. PHP Houses 3.3. Formalization of Areas | Mmakau, Mangopeng, Selosesha, New Town, Mashiapere, Thlopane, Block 7, All areas |
| 6. LED | 6.1.EPWP/CWP 6.2. SMME’s | 6.3. Complex / Mall |  |  |  |  |
| WARD 17 |  |  |  | 4. Social Services | 4.1 Clinic 24 hours 4.2. Upgrade of all sports grounds 4.3. Library 4.4. Skills Centre 4.5. Maintenance of recreational facilities | All sections All areas |
| NEEDS | PROJECTS | AREA |  |  |  |  |
| 1.Roads & Storm water | 1.1. Storm water Drainage 1.2. Tarring of main roads 1.3. Re-gravelling of access roads 1.4. Speed humps | All areas with tarred roads in Mapetla, Ramogodi, Polonia, Mangopeng, Newtown Ramogodi, Polonia Mapetla, Ramogodi, Polonia, Mangopeng, Newtown |  |  |  |  |
|  |  |  |  | 5. LED | 5.1 Skills Development 5.2 Industrial Park 5.3.Car Wash 5.4 Industrial area for skills |  |
| 2. Land and Housing | 2.1. RDP Houses 2.2. PHP Houses 2.3. Formalization of Rural Areas | Mapetla, Ramogodi, Polonia, Mangopeng, Newtown |  |  |  |  |
|  |  |  |  | EXCESS NEEDS |  |  |
|  |  |  |  | Social Services | 4.6. Disability Centre |  |
| 3. Electricity | 3.1. High Mast Lights x10 3.2. House Connections 3.3. Street Lights 3.4. Solar geyser and solar high mast light |  |  |  |  |  |
|  |  |  |  | 6. Electricity | 6.1. Yard Connections 6.2. High Mast Lights |  |
| 4. Water & Sanitation | 4.1. Reservoir 4.2. Sewage system | All outstanding areas in Mapetla, Ramogodi, Polonia, Mangopeng |  | WARD 19 |  |  |
|  |  |  |  | NEEDS | PROJECT | AREAS |
| 5. Social Services | 5.1. Multipurpose centre 5.2. Mobile Clinic 5.3. Sports facilities 5.4. Disability Centre 5.5. Middle & High Schools | Ramogodi Mapetla, Polonia, Newtown(Blue Birds) Ramogodi Ramogodi & Mapetla |  | 1. Road and Storm water | 1.1. Access Roads 1.2. Roads and Storm | Tshwara, Springs, Channelview, Blackrock, Mathathaneng, Mou-mong, Dekroon, Moagi & Newtown |
|  |  |  |  | 2. Electricity | 2.1. High mass light 2.2. Electric connection to Houses | All areas Moagi section (next to Motlhake Primary school area) |
| EXCESS NEEDS |  |  |  |  |  |  |
| 6. LED | 6.1 Nursery 6.2 Car wash | 6.3. Pig Farming & Poultry |  | 3. Water and sanitation | 3.1 Sewage system 3.2 Toilets 3.3. Water | All areas |
|  |  |  |  | 4. Land and Housing | 4.1 RDP Houses 4.2 Formalization of Rural Area | All areas |
| WARD 18 |  |  |  |  |  |  |
| NEEDS | PROJECTS | AREA |  | 5. Social Services | 5.1 Clinic (24/7) 5.2 Police Station 5.3 Ambulance and Fire Vehicle | All areas |
| 1. Roads & Storm water | 1.1. Paving of all access roads 1.2. Regravelling of internal roads 1.3. Gravelling of access roads 1.4. Speed humps | All Areas |  |  |  |  |
|  |  |  |  | EXCESS NEEDS |  |  |
|  |  |  |  | 6. LED | 6.1 Industrial Park (Skills) – All areas |  |
| 2. Water & Sanitation | 2.1. Clean Purified tap water 2.2. Maintenance of existing Boreholes 2.3. Meter installations in all Areas 2.4. Bulk Water Supply 2.5. Sewage system | Mmakau, Mangopeng, Selosesha, New Town, Mashiapere, Thlopane, Block 7, Ramalong, Naledi Futha, Roma and Ninive |  |  |  |  |

| WARD 20 |  |  |  |  |  | WARD 21 (Cont) |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| NEEDS |  |  | PROJECT | AREAS |  | NEEDS | PROJECTS | AREAS |
| 1. Roads & Storm Water |  |  | 1.1. Tarring or paving main internal roads 1.2. Proper storm water drainage water network 1.3. Speed Humps 1.4. Street names 1.5. Grading – regravelling, upgrading | Mothotlung, Section (A) Mothotlung, Mothotlung |  | 2. Water & Sanitation | 2.1. Upgrading of Sewerage 2.2. Refurbishment of leaking reservoir | Damonsville Damonsville |
|  |  |  |  |  |  | 3. Electricity | 3.1. Additional High Mast Light 3.2. Yard Connections 3.3. Street light maintenance 3.4. Replace underground cable with overhead line 3.5. Network upgrading | Mothotlung Ext. 1 & 2 Damonsville Damonsville X2 Damonsville Mothotlung Ext. 1 & 2 |
| 2. Water & Sanitation |  |  | 2.1. Additional Reservoir. 2.2. Water installation pipe line to cemetery 2.3. Cement portable toilets at Cemetery 2.4. New water & sanitation network 2.5. Ablution block at cemetery | Mothotlung |  |  |  |  |
|  |  |  |  |  |  | 4. Land & Housing | 4.1 Land 4.2. RDP Houses 4.3. Title Deeds 4.4. PHP Houses 4.5. Formalizing of Informal Settlements | Mothotlung Ext. 1 & 2 Damonsville & Mothotlung Ext. 1 & 2 Damonsville & Mothotlung Ext 1 & 2, Damonsville Damonsville |
| 3. Land & Housing |  |  | 3.1. Land 3.2. Title Deeds 3.3. Infrastructure(2500) RDP Houses 3.4. Land for property dev site 3.5. Assessment of RDP | Mothotlung |  | 5. Social Services | 5.1. Taxi Rank 5.2. Upgrading of Library 5.3. Schools High & Primary 5.4. Clinic 5.5. CCTV Camera | Damonsville Damonsville Mothotlung Ext. 1 & 2 Mothotlung Ext. 1 & 2 Mothotlung Ext. 1 & 2 |
| 4. Electricity |  |  | 4.1. Street lights 4.2. Additional high mast light 4.3. Solar geysers. 4.4. Uplifting of crossing electric cables network 4.5. Electric network upgrading. | Mothotlung Section (A) Mothotlung Section (A) Section (A) Mothotlung, Section (A) Mothotlung, |  | EXCESS NEEDS |  |  |
|  |  |  |  |  |  | 6. LED | 6.1. Youth Skills Development Centre 6.2 Hawkers Facilities 6.3 Agricultural Development | 6.4. Tourism Business Development 6.5. Business Complex 6.6. EPWP to assist at the roads |
| 5. Social Services |  |  | 5.1. Police Station 5.2. Cement palisade fence at cemetery. 5.3. Paving of internal roads at cemeteries. 5.4. Old Age Home 5.5. Sports Grounds |  |  | WARD 22 |  |  |
|  |  |  |  |  |  | NEEDS | PROJECTS | AREAS |
|  |  |  |  |  |  | 1. Land & Housing | 1.1 Provide housing 1.2 Acquisition of Land for Business sites & Housing 1.3 Affordable housing near Elandsrand | Corri Sanders, Siatlala, Green side Corri Sanders, Siatlala, Green side |
|  |  |  |  |  |  | 2. Roads & Storm water | 2.1 Paving of internal roads 2.2 Construction of all access roads 2.3.Speed humps / rumble sticks 2.4 Upgrading of existing roads (in- cluding speed humps & side walks) 2.5. Re-gravelling of internal roads where there are no tarred roads | All internal roads that are not tarred Old Oukasie – All roads Robot cnr Van Deventer & Gert Scheepers and between Siatlala and Corrie Sanders Oukasie and Blinkblaar Street in Bodenstein Park Green side all internal roads, Phase 2 & 3 |
| EXCESS NEEDS |  |  |  |  |  |  |  |  |
| 5. Social Services |  |  | 5.6. Development of 24/7 Clinic 5.7. Youth Centre | 5.8. Multi Purpose Sports grounds |  |  |  |  |
| 6. LED |  |  | 6.1. SMME’s Skills Development 6.2. Co-operatives, NGO, youth and women, free registration of SMME’s 6.3. SMME Seda training as per 6.2. (grants available from Department Co- operative) |  |  |  |  |  |
|  |  |  |  |  |  | 3. Electricity | 3.1. High mast lights 3.2. Replacement of corroded electricity Poles 3.3. Replacement of tattered electric boxes in streets | Robot cnr Van Deventer & Gert Scheepers Street, Brits, Green side, Corri Sanders, Phase 3 and Soccer field Blinkblaar Street, Bodenstein Park Bodenstein Park Brits |
| WARD 21 |  |  |  |  |  |  |  |  |
| NEEDS |  |  | PROJECTS | AREAS |  |  |  |  |
| 1. Roads & Storm water |  |  | - Regravelling of Internal Roads - Paving main Internal Roads - Proper Stormwater drainage network - Stop Sign | Mothotlung Ext. 1 & 2 Damonsville |  |  |  |  |

| WARD 22 (Cont) |  |  |  | WARD 23 (Cont) |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| NEEDS | PROJECTS | AREAS |  | NEEDS | PROJECTS | AREAS |
| 4. Water & Sanitation | 4.1. Rehabilitation of Existing Sewage System 4.2 Yard connections 4.3 Water Tanks x 3 4.4 Sewage pumps 4.5 Mobile toilets additional | Oukasie Original: G-Side, North Camp and Masenkeng Masepala Phase 3 / Block 5 Brits Corri Sanders |  | 3. LED | 3.1. Upgrading of Taxi Rank 3.2. Small Town Regeneration 3.1. Formalization, upgrading and refurbish- ment of hawkers . | Behrens and Pretoria taxi rank Brits CBD and entrance to town Murray Ave, Railway St and Tom St |
|  |  |  |  | 4. Electricity | 4.1. Street lights | Entire Primindia and Lights facing towards river, River Walk St |
| 5.Social Services | 5.1 Emergency services 5.2 Day care centres 5.3 Library 5.4 Youth dev centre 5.5 Development of Sporting Facility | Next to Library Botlhabelo High School, Block I Primary school, block 1 |  | EXCESS NEEDS |  |  |
|  |  |  |  | Social Services | 2.6. Upgrade of Brits Town Hall |  |
|  |  |  |  | WARD 24 |  |  |
|  |  |  |  | NEEDS | PROJECTS | AREAS |
| EXCESS NEEDS |  |  |  | 1. Water & Sanitation | 1.1. Yard Connections 1.2. Sewer System 1.3. Stand Pipes 1.4. Boreholes 1.5. Addition of Water Truckers | Sofasonke, Ndlovu & Mashamplani Sofasonke, Ndlovu, Mashamplani & Lekgema Sofasonke, Ndlovu, Mashamplani & Lekgema All Sections |
| 6.LED | 6.1 Agricultural Projects 6.2 Cultural Village 6.3 Poultry Farming | Identified municipal farm next to Oukasie Next to Botlhabelo High school Identified municipal farm next to Oukasie |  |  |  |  |
| 2. Roads & Storm water | 2.6 Storm Water Drainage & Manholes 2.7 Expansion of Road 2.8 Upgrade of Road & Bridge 2.9 Fencing of Danie Street at cul de sac | Old Oukasie Brits to Letlhabile Fruit & Veg till after bridge |  |  |  |  |
|  |  |  |  | 2. Roads & Storm water | 2.1. Storm water drainage 2.2. Bus Route Mashamplani 2.3. Construction of a bridge 2.4. Tarring/Reseal of Provincial Road (Oskraal to Klipgat) 2.5. Speed Humps | Entire Ward, Klipgat B & C, Sofasonke, Tophasha Klipgat B & C Ikaneng, Sofasonke, Ndlovu Sofasonke, Ndlovu, Mashamplani & Lekgema Ndlovu to the Main Roads |
| 5. Social Services | 5.6. Complete closure of canal (Green side, Phase 2 & 3) 5.7. Erection of cameras on all outgoing roads 5.8. Traffic control after 17:00 (Traffic signs) 5.9. Formalization of Hawkers (Phase 2 & 3) 5.10. Clinic 5.11. Upgrading of Licensing Centre (RA & DLTC) |  |  |  |  |  |
|  |  |  |  | 3. Land & Housing | 3.1. Acquisition of Land for Tenants & Formallisation Process & Title Deeds 3.2. RDP Houses 3.3. Rural Subsidy Houses 3.4. Industrial Site | Phasha, Ikageng, Ndlovu All Areas All Areas Klipgat B |
| WARD 23 |  |  |  | 4.Electricity | 4.1. Yard Connections | Ndlovu, Makanyane & Lekgema |
| NEEDS | PROJECTS | AREAS |  | 5. Social Services | 5.1. Clinic 5.2. Community Health Centre with Fence 5.3. Cemetery with Fence 5.4. Building of Fire Station 5.5. Multi-Purpose Centre with Library | Klipgat B & C Klipgat B Klipgat C Klipgat C Klipgat A, B & C |
| 1. Roads & Storm water | 1.1. Roads 1.2. Street signs 1.3. Stormwater drains (should be redone and have mesh in front of the drain | Brug St, Carel St, Central St, Jacaranda Ave, Crocodile St, Tom St, Hajee St, Roshnee Place, Sunrise Rd, Rose Ave, Willow Crescent, Protea Crescent, Daisy St, River Walk St, Park St, Murray Ave, Railway St and Kretchmar St |  |  |  |  |
|  |  |  |  | EXCESS NEEDS |  |  |
|  |  |  |  | 2 Roads & Storm water | 2.6. Internal Roads |  |
| 2. Social Services | 2.1. Concrete palisade 2.2. Bus Shelter 2.3. Upgrade of Primindia Town hall 2.4. Upgrade of Primindia sports centre (sports grounds, tennis courts swimming pools, netball courts, picnic area) 2.5. Upgrade of Park | Canal, Jakaranda Ave, Hajee Street Park, Jacaranda Ave opposite Central Primary School Primindia Primindia Sports Centre Hajee Street Park |  |  |  |  |
|  |  |  |  | 5. Social Services | 5.6. Taxi Rank 5.7. Park |  |
|  |  |  |  | 6. LED | 6.1. WIFI Connections 6.2. Agriculture 6.3. Poverty Alleviation Programme & EPWP 6.4. Skills Development | 6.5. Car Wash 6.6. Rehabilitation Centre 6.7. Food Parcels for Orphans |
| WARD 25 |  |  |  | WARD 26 (Cont) |  |  |
| NEEDS | PROJECTS | AREAS |  | NEEDS | PROJECTS | AREAS |
| 1. Land & Housing | 1.1. Low Cost & Economic Houses (RDP & PHP) 1.2. Acquisition of Title Deeds 1.3. Acquisition of Land for Housing/ Industrial 1.4. Site & Graveyard 1.5. Upgrading of cemeteries | Bokfontein, Bapong Bokfontein Bokfontein Bapong |  | 5. Water & Sanitation | 5.1. Sewerage System (Lonmin approached the community and said they can utilize their system) | Wonderkop and Ext. 2 |
|  |  |  |  | EXCESS NEEDS |  |  |
|  |  |  |  | 6. Social Services | 6.1. 24 hr Clinic 6.2. Taxi rank not completed 6.3. Security in Wonderkop School (Rakgatla) | 6.4. Fencing of cemetery 6.5. Library 6.6. Police Station |
| 2. Roads & Storm water | 2.1. Upgrading of storm water drainages 2.2. Tarring of Main Roads & bus route 2.3. Speed humps & road signs 2.4. Paving of Roads | Bapong Bokfontein Bokfontein, Zandfontein, Bapong Bokfontein & Bapong |  |  |  |  |
|  |  |  |  | WARD 27 |  |  |
|  |  |  |  | NEEDS | PROJECTS | AREAS |
| 3. Electricity | 3.1. Installation of household electrification 3.2. Upgrading & Construction of Sub Stations 3.3. High Mast Lights x 36 3.4. Street lights | Legalaopeng, Bokfontein, Skoolplaas Bapong Legalaopeng, Bokfontein, Newtown, |  | 1. Water & Sanitation | 1.1. Water Borne Toilets 1.2. Water Yard Connections | Bokamoso, Loekeng |
|  |  |  |  | 2. Roads & Stormwater | 2.1. Paving of internal roads & side walks 2.2 Sealing of potholes | Bokamoso, Loekeng Mooinooi |
|  |  |  |  | 3. Social Services | 3.1 Cemetery 3.2. Clinic | All Areas |
| 4. Water & Sanitation | 4.1. Yard Connections 4.2. Water Reticulation 4.3. Construction of Water Borne Toilets 4.4. Borehole with tanks | Legalaopeng, Newtown, Skoolplaas, Oustad Legalaopeng, Newtown, Skoolplaas, Oustad Legalaopeng, Bokfontein, Newtown, Oustad Legalaopeng Bokfontein, Newtown, Oustad |  |  |  |  |
|  |  |  |  | 4. Land & Housing | 4.1. Speeding up development process 4.2. Formalization | Portion 34 Bokamoso Bokamoso |
|  |  |  |  | 5. Electricity | 5.1. High Mast Lights 5.2. Street Lights | Extension 13 Mooinooi, Bokamoso, Loekeng |
| 5. Social Services | 5.1. Construction of Clinic 5.2. Satellite Police Station 5.3. Pensioners Pay Point 5.4. Construction of School | Bokfontein Bokfontein, Bapong Bokfontein Bokfontein |  |  |  |  |
|  |  |  |  | EXCESS NEEDS |  |  |
|  |  |  |  | 6. LED | 6.1. Skills Development Centre 6.2. Agricultural Projects |  |
| EXCESS NEEDS |  |  |  |  |  |  |
| 6. LED | 6.1. Job Creation 6.2. Skills Development 6.3. Agricultural Projects 6.4. Detergent Project (soap) | 6.5. Skills Development Centre 6.6. Library 6.7. Recreation Centre 6.8. Youth development (sports & culture) |  |  |  |  |
|  |  |  |  | WARD 28 |  |  |
|  |  |  |  | NEEDS | PROJECTS | AREAS |
|  |  |  |  | 1. Water & Sanitation | 1.1. Toilets at Cemeteries 1.2. Water Connections 1.3. Toilets at Taxi Rank | All Areas |
| WARD 26 |  |  |  |  |  |  |
| NEEDS | PROJECTS | AREAS |  |  |  |  |
| 1. Land & Housing | 1.1. Acquisition of Land 1.2. RDP Houses 1.3. Land for Churches | Wonderkop and Ext 2 |  | 2. Roads & Stormwater | 2.1. Tarring of Bus Road 2.2. Paving of Internal Roads 2.3. Speed Humps and Road Signs 2.4. Backfilling of Internal Roads 2.5. Bridge and culvert | Bapong and Sjandav All roads |
| 2. Roads & Storm water | 2.1. Paving of Internal Roads 2.2. Storm Water Drainage 2.3. Patching of Potholes 2.4. Repair of Road | Wonderkop and Ext 2 Segwaelane to Wonderkop Primary School |  |  |  |  |
|  |  |  |  | 3. Electricity | 3.1. High Mast Lights 3.2. House Connections | All Areas Bapong |
| 3. Electricity | 3.1. Energizing of Apollo Lights 3.2. Expansion of Sub-Station | Wonderkop and Ext 2 |  | 4. Land & Housing | 4.1. Land Acquisition 4.2. Housing Formalization 4.3. RDP Houses | All Areas |
| 4. LED | 4.1. Skills Development and Training 4.2. Brick Making Project | Wonderkop and Ext 2 |  |  |  |  |

| WARD 28 |  |  |  | WARD 30 |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| NEEDS | PROJECTS | AREAS |  | NEEDS | PROJECTS | AREAS |
| 5. LED | 5.1. Skills Development 5.2. Cattle Camp 5.3. SMME’s 5.4. Agriculture | 5. LED |  | 1. Roads & Storm water | 1.1.Upgrading/Tarring /Sealing of all roads 1.2. Pavement of pathways for pedestrians 1.3. Speed humps on R514 1.4. Upgrade and construction of curbing, storm water drainage system and litter traps 1.5. Tarring of road (S66) | Whole Ward Refentse & Ten Rooms R511 – Ifafi, Melodie and Meerhof Meerhof/Ifafi Rd Ten Rooms |
| EXCESS NEEDS |  |  |  |  |  |  |
| 6. Social Services | 6.1. Police Station 6.2. 24 hrs Clinic 6.3. Multipurpose Centre | 6.4. Youth Centre 6.5. Sports, Art & Culture |  |  |  |  |
|  |  |  |  | 2. Water & Sanitation | 2.1. Upgrading of water pipes 2.2. Upgrading of sanitation pipes 2.3. Fencing of Sewage Plant 2.4 Upgrading of sewage plant 2.5. Upgrade and install of water meters | Whole Ward Refentse Sunway Village Rietfontein Whole Ward |
| WARD 29 |  |  |  |  |  |  |
| NEEDS | PROJECTS | AREAS |  |  |  |  |
| 1. Land & Housing | 1.1 Acquisition and Development of Land 1.2. PHP Houses 1.3. RDP Houses | All Areas Poland (CPA) Shamburg, Orange Farm & Sangiro |  | 3.Social Services | 3.1. Upgrading of Clinic building 3.2 Mobile Clinic 3.3 Skips for waste and weekly removal 3.4. High School 3.5. Community Hall | Schoemansville Sunway Village Ten Rooms, Refentse & Sunway Village Sunway Village Sunway Village |
| 2. Water & Sanitation | 2.1. Boreholes with tanks (Magalies Water to provide) 2.2. Upgrade of current water pipes 2.3. Water Tankers 2.4. Bulk Pipeline | All Areas All Areas All Informal settlements |  |  |  |  |
|  |  |  |  | 4. Electricity | 4.1. Cut trees in Town overhead cables 4.2. Erecting of high mast lights 4.3. New Substation & backup system as per feasibility study 4.4. Electricity on R513 | Meerhof, Ifafi and Melodie Refentse & Sunway Village Ifafi Sunway Village & Refentse |
| 3. Electricity | 3.1. Electricity Installation 3.2. Upgrading of current infra- structure 3.3. Apollo Lights | Sangiro and Orange Farm All Areas Shamburg & Poland |  |  |  |  |
|  |  |  |  | 5. Land & Housing | 5.1. Phase 2 of Sunway Village need to be implemented with services 5.2. Removal and relocation of illegal squatters at 10 Rooms |  |
| 4. Social Services | 4.1. 24h Clinic 4.2. Multipurpose & Skills Develop- ment Centre | All Areas All Areas |  |  |  |  |
|  |  |  |  | EXCESS NEEDS |  |  |
| 5. LED | 5.1. Job Creation (Business em- powerment, small business establishment 5.2. Skill Development (Training on Tourism) | All Areas |  | Roads & Stormwater | 1.6. Broaden Road Between Melodie and Jasmyn |  |
|  |  |  |  | Water & Sanitation | 2.6. Additional reservoir in Meerhof (at least 10 m/l) |  |
| EXCESS NEEDS |  |  |  | Social Services | 3.6. Complete closure of canal 3.7. Erection of cameras on all outgoing roads 3.8. Traffic control after 17:00 (Traffic signs) |  |
| 6. Roads & Storm water | 6.1. Upgrade of road 6.2. Speed humps 6.3. Regravelling of road 6.4. Tarred road | Kommandonek, Kosmos & Poland All areas Shamburg, Sangiro, Hartbeeshoek & Skeerpoort, Skeerpoort to Broederstroom, Kosmos |  |  |  |  |
|  |  |  |  | WARD 31 |  |  |
|  |  |  |  | NEEDS | PROJECTS | AREAS |
|  |  |  |  | 1. Land & Housing | 1.1. Land Acquisition for housing & cemetery 1.2. PHP & RDP Houses | Portions 28 & 29 Buffelsfontein farm 465 JQ, Modderspruit All areas |
|  |  |  |  | 2. Roads & Storm water | 2.1. Paving of main internal roads 2.2. Re-graveling of internal roads | From R104 to Sereopark, Majaka-neng, Old road to the mortuary All areas |
| WARD 31 (Cont) |  |  |  | WARD 33 |  |  |
| NEEDS | PROJECTS | AREAS |  | NEEDS | PROJECTS | AREAS |
| 3. Social Service | 3.1. Construction of new cemetery 3.2. Upgrading of sports field 3.3. Fencing of existing cemeteries 3.4. Technical High School 3.5. Community park | To the required land Phase 2 Modderspruit Modderspruit |  | 1. Land & Housing | 1.1. Land Acquisition 1.2. Formalizing Townships (Erven and streets) 1.3. Formalizing / secure land tenure 1.4. Formalizing housing typology (RDP & PHP Houses) | Wawiel, Mahantjie, Shieling, Zandfontein and Damdoryn |
| 4. Water & Sanitation | 4.1. Infrastructure Development 4.2. House connections 4.3. Proper Sewer System | Katlegong Ext All areas from Safropa Mangoes, Sereo Park All areas |  |  |  |  |
|  |  |  |  | 2. Water & Sanitation | 2.1. Proper water and sanitation networks 2.2. Upgrade of sewer plant 2.3. Drilling of Boreholes 2.4. Installation of VIP toilets 2.5. Water tanks | Wawiel, Mahantjie, Shieling, Zand-fontein, Damdoryn, Schoemansville, Part of Melodie A/H, Wawiel, Mahantjie, Shieling, Zandfontein and Damdoryn Wawiel, Mahantjie, Shieling, Zand-fontein and Damdoryn Wawiel, Mahantjie, Shieling, Zand-fontein and Damdoryn Wawiel, Mahantjie, Shieling, Zand-fontein and Damdoryn |
| 5. Electricity | 5.1. Infrastructure Development 5.2. House Connections 5.3. High Mast Lights (Increase) | Nkandla and Malema View Katlegong All areas: 3 Safropa, 2 Mangoes, 1 Skierlik, 1 Sereo-park & 1 Thabeng |  |  |  |  |
| EXCESS NEEDS |  |  |  |  |  |  |
| 6. LED | 6.1. Skills Development 6.2. Entrepreneurial Skills |  |  |  |  |  |
| 3. Social Service | 3.6. Multipurpose Centre |  |  |  |  |  |
|  |  |  |  | 3. LED | 3.1. Depending of hierarchy of roads within formalized townships (Dirt roads, Gravel roads, Tar roads) 3.2. Rehabilitation and reseal of all roads 3.3. Proper storm water drainage and Curbing 3.4. Speed humps, warning signs and height restriction 3.5. Erection of new traffic signs | Wawiel, Mahantjie, Shieling, Zand-fontein and Damdoryn, Schoemansville, Part of Melodie A/H Wawiel, Mahantjie, Shieling, Zand-fontein, Schoemansville and Part of Melodie A/H Schoemansville and Part of Melodie A/H, Damdoryn, Schoemansville and Part of Melodie A/H Schoemansville and Part of Melodie A/H |
| WARD 32 |  |  |  |  |  |  |
| NEEDS | PROJECTS | AREAS |  |  |  |  |
| 1. Roads & Storm Water | 1.1. Main Road 1.2. Paving of Internal Roads | Mshengu All Areas in Ward |  |  |  |  |
| 2. Electricity | 2.1. Apollo Lights (20) 2.2. House Connections | Segwaelane |  |  |  |  |
| 3. Water & Sanitation | 3.1. Toilets 3.2. Upgrading of Reservoir 3.3.Pressure Pumps | Segwaelane |  |  |  |  |
|  |  |  |  | 4. Electricity | 4.1. Yard Connections 4.1.Upgrade of network 4.2. High Mast Lights 4.3. Upgrade Street lighting | Wawiel, Mahantjie, Shieling, Zandfontein, Damdoryn, Schoemansville and Part of Melodie A/H |
| 4. Land & Housing | 4.1. RDP Housing 4.2. Title Deeds | Segwaelane Skoonplaas |  |  |  |  |
| 5. Social Services | 5.1 24h Operational Clinic 5.2. Taxi rank | 5. Social Services |  | 5. Social Services | 5.1. Mobile/Permanent Clinics 5.2. Upgrading of existing Clinic 5.3. Taxi / Bus Ranks 5.4. Sport Facilities 5.5. Day care centres, Primary and High School | Wawiel, Mahantjie, Shieling, Zand-fontein and Damdoryn Schoemansville Damdoryn Hartbeespoort Sports Grounds, Wawiel, Mahantjie, Shieling, Zand-fontein, Damdoryn Wawiel, Mahantjie, Shieling, Zandfontein, Damdoryn |
| EXCESS NEEDS |  |  |  |  |  |  |
| 6. LED | 6.1. EPWP Program – All Areas |  |  |  |  |  |

| WARD 33 EXCESS NEEDS |  |  |  | WARD 35 |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| 6. Public Safety | 6.6. Upgrade waste removal 6.7. Upgrade Public Transport facilities 6.8. Mobile Police Station | 6.9. Traffic Calming within road reserves 6.10. Daily traffic law enforcement 6.11. Upgrade / maintenance of Fire Hydrants |  | NEEDS | PROJECTS | AREAS |
|  |  |  |  | 1. Water & Sanitation | 1.1 Boreholes 1.2 Jojo Tanks 1.3 Yard connection 1.4 Mini Reservoir | Oskraal, Rabokala, Kgablatsane Green side, Oskraal, Rabokala All areas Oskraal, Rabokala |
| 7. LED | 7.1. Sustainable Job Creation via the use of local labor instead of labor from the outside area 7.2. Skills development / formal training centers (operational daily) |  |  |  |  |  |
|  |  |  |  | 2. Roads & Stormwater | 2.1 Storm water Drainage 2.2 Re-tarring of main road 2.3. Speed humps 2.4. Tarred link road 2.5. Upgrading of Road (2 km) to be paved/ tarred | All areas Oskraal 2604, Rabokala Road All areas Between Okraal and Rabokala Kgabalatsane Morolong Interval rd, Oskraal, Rabokala |
| WARD 34 |  |  |  |  |  |  |
| NEEDS | PROJECTS | AREAS |  |  |  |  |
| 1. Water & Sanitation | 1.1. Sanitation 1.2. Prepaid water meters 1.3. Bulk Pipe 1.4. Refurbishment Boreholes | Shakung, Moiletswana, Madinyane, Baika-gedi, Ramogatla, Letlhakaneng, Rietview, Dimpongpong Shakung, Moiletswana, Madinyane, Baika-gedi, Ramogatla, Letlhakaneng, Rietview, Dimpongpong Ramogatla, Malerato |  | 3. Land & Housing | 3.1. PHP houses 3.2. Land acquisitions for housing & cemetery 3.3. RDP houses 3.4 Formalisation of Rural Areas 3.5 Land for Affordable Houses | Oskraal (250), Rabokala (500), Morolong Sect, Kgablatsane (500), Thetele (250), Switch (200), Rankotea (150), Ntswapilong (100) All areas All areas Oskraal, Rabokala, Morolong Sect, Kgablatsane Thetele, Rankotea & Switch |
| 2. Roads & Stormwater | 2.1. Tarring of Road 2.2. Upgrading & Re-gravelling Internal Roads 2.3. Road signs (bridge and curves) 2.4 .Upgrading of Provincial Roads & Access Roads 2.5. Speed Humps | Road D602 Shakung, Moiletswana, Dipompong Moiletswana, Shakung, Dipompong Moiletswana and Mmulakgoro Rietview, Letlhakaneng |  |  |  |  |
|  |  |  |  | 4. Electricity | 4.1 Extentions 4.2 House connections 4.3 High mast lights 4.4.Solar Geysers | All areas All areas All areas All areas |
|  |  |  |  | 5. Social Services | 5.1. Crime prevention 5.2 Schools 5.3 Clinic 5.4 Library 5.5 Crèche | All areas All areas Oskraal, (need upgrading & 24 hrs service Rabokala) All areas All areas |
| 3. Land & Housing | 3.1. PHP Houses 3.2. Formalization 3.3. RDP Houses | All Areas Malerato, Rietview, Dipompong, Madinyane, Shakung, Moiletswana |  |  |  |  |
| 4. Electricity | 4.1 Apollo Lights 4.2. Building & Upgrading of New Substation 4.3 Electricity Extension | Shakung,Madinyane,Moiletswana,Dipompong, and one at each school, Madinyane Malerato Extension |  | EXCESS NEEDS |  |  |
|  |  |  |  | 6. LED | 6.1 Vegetable Gardens – All areas 6.2 Cattle farming – All areas 6.3 Chicken Farming – All areas 6.4 Goat Farming – All areas | 6.5 Tourism Site/ Eco Tourism 6.6 Shopping Mall – All areas 6.7 Irrigation Systems 6.8 Old age home – All areas |
| 5. Social Services | 5.1 Clinic 5.2 Upgrading of cemeteries 5.3 Hospice with VIP toilets 5.4 Post office 5.5 Schools | Letlhakaneng, Madinyane Ext, Dimpompong, Madinyane,Moiletswana, Shakung, Letlha-kaneng, Madinyane Ext, Dimpompong, Madinyane, Moiletswana, Shakung, Letlhakaneng, Shakung Shakung, Letlakaneng, Moiletswana,Malerato and Rietview |  |  |  |  |
|  |  |  |  | 2. Roads & Stormwater | 2.6 Upgrading of 8.5 km road linking Rabokala & Oskraal 2.7 Paving of Roads at school and clinic |  |
|  |  |  |  | 5. Social Services | 5.6 Youth dev centre 5.7 Park/ Sports Ground - All areas 5.8 Hall - All areas |  |
| EXCESS NEEDS |  |  |  |  |  |  |
| 6. LED | 6.1. Farming Activities |  |  |  |  |  |
| Social Services | 5.6. Community Hall - Letlhakaneng 5.7. Construction of Parks 5.8. Dumping Site | 5.9. Old Age Home 5.10. Disability Care Centre |  |  |  |  |
| WARD 36 |  |  |  | WARD 37 (Cont) |  |  |
| NEEDS | PROJECTS | AREAS |  | NEEDS | PROJECTS | AREAS |
| 1. Water & Sanitation | 1.1. Water supply 1.2. Audit in all projects | Klipgat |  | 3. Roads & Storm water | 3.1. Stormwater Road 3.2. Regravelling of Roads 3.3. Paving of Internal Roads 3.4. Stormwater Drainage 3.5. Maintenance of Stormwater & Roads | Klipgat, Ikageng, 2010, Langalibalele and Hillside All Section All Section Klipgat Klipgat |
| 2. Electricity | 2.1. High Mast Lights 2.2. Street lights 2.3. Budget for maintenance | Klipgat |  |  |  |  |
| 3. Roads & Storm water | 3.1. Storm water drainage 3.2. Construction of bridge 3.3. Pavement of Internal Roads 3.4. Speed Humps | Klipgat |  |  |  |  |
|  |  |  |  | 4. Land & Housing | 4.1. Formalization\ 4.2. RDP Houses 4.3. PHP Houses 4.4. Title Deed | Ikaneng, 2010, Hillside, Langalibalele, John Dube Klipgat All SectionsKlipgat, Ikaneng Section |
| 4. Land & Housing | 4.1. Formalization 4.2. Title Deeds 4.3. RDP Houses | Klipgat Klipgat1 |  |  |  |  |
|  |  |  |  | 5. Social Services | 5.1. 24h Clinic 5.2. Fire Station 5.3. Park | Klipgat |
| 5. Social Services | 5.1. Community Health Care (mobile clinic) 5.2. Library access to free Wi-Fi 5.3. Fire Station (meanwhile a fire tanker) 5.4. Parks 5.5. Municipal service point | Klipgat |  |  |  |  |
|  |  |  |  | EXCESS NEEDS |  |  |
|  |  |  |  | 6. LED | 6.1. Youth Programme 6.2. Agricultural Project 6.3. Building Skills Development and Recycles | 6.4. SMME Development 6.5. Heritage Museum |
| EXCESS NEEDS |  |  |  |  |  |  |
| 5. Social Services | 5.6. Police Patrol |  |  | WARD 38 |  |  |
|  |  |  |  | NEEDS | PROJECTS | AREAS |
| 6. LED | 6.1. Capacity Building (Skills Development) & Recycling 6.2. Youth Projects 6.3. SMME’s Development – Klipgat | 6.4. Agricultural Projects 6.5. Heritage & Museum 6.6. Hawkers Pavillion |  | 1. Land & Housing | 1.1. Township Development of Plots 1.2. Finalization of Informal Settlement 1.3. RDP Houses 1.4. Affordable Stands (5,000 stands/ houses) | Oskraal Block H Block H, Plots Oskraal Block H, Nooitgedacht Plot JQ 242 |
| WARD 37 |  |  |  | 2. Electricity | 2.1. Solar Geysers 2.2.Hight Mast Lights | Centreville Plots Oskraal |
| NEEDS | PROJECTS | AREAS |  |  |  |  |
| 1. Electricity | 1.1. Electrification 1.2. High Mast Lights 1.3. Maintenance of existing High Mast Lights | 2010, Hillside, Langalibalele All Section |  | 3. Roads & Storm water | 3.1. Upgrade of Internal Roads 3.2. Speed Humps 3.3. Regravel Roads | Mohlasedi, Maqakamba, Motaung, Selome, Mahlangu, and Motau streets (10 km of internal roads) Block E and F and Plots Oskraal Block E and F and Plots Oskraal |
| 2. Water & Sanitation | 2.1. Yard Connection 2.2. Sewer System 2.3. Stand Pipe 2.4. Boreholes | 2010, Hillside, Langalibalele Ikaneng, 2010, Hillside, Langalibalele & Klipgat Hillside, 2010, Langalibalele All Section |  |  |  |  |
|  |  |  |  | 4. Social Services | 5.1. High School 5.2. Clinic 5.3. Sport Facilities 5.4. Community Hall | Block E and F |
|  |  |  |  | 5. Water & Sanitation | 5.1. Boreholes 2.2. Jojo Tanks | Blocks E and F, Plots Oskraal Plots Oskraal |
|  |  |  |  | EXCESS NEEDS |  |  |
|  |  |  |  | 6. LED | 6.1. Creation of employment through cleaning of manholes and streets, Youth projects to address drugs (naupe) |  |

| WARD 39 |  |  |  | WARD 40 (Cont) |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| NEEDS | PROJECTS | AREAS |  | 3. Roads & Storm water | 3.1. Upgrading of stormwater drainages 3.2. Regravelling and paving of internal Roads and Speed Humps 3.3. Tarring of Provincial roads (D1262) | Sonop, Segwaelane, Regorogile, Khalamtwana Sonop, Segwaelane, Regorogile, Khalamtwana, Pansdrift/ Rooikoppies Greenstore, Rooikoppie, Kareepoort |
| 1. Land & Housing | 1.1. RDP Houses (2,500) 1.2. Formalizing of informal settlements 1.3. Development and allocation of stands 1.4. Land Transfer and Title Deeds 1.5. Allocation of Church Stands | Mamogalieskraal and Vuka Section Elandsrand |  |  |  |  |
|  |  |  |  | 4. Water & Sanitation | 4.1. House connections 4.2. Revamping of sewer 4.3. Water reticulation | Regorogile, Sonop, Segwaelane, Khalamtwana Sonop Regorogile, Segwaelane, Khalamtwana |
| 2. Electricity | 2.1. Legal connections 2.2. Replace underground cabling with overhead Line 2.3. Lighting of parks and streets 2.4. Additional lighting | Elandsrand, Mamogalieskraal and Vuka Section |  |  |  |  |
|  |  |  |  | 5. Social Services | 5.1. English medium school 5.2. Rehabilitation centre for drug users 5.3. Community Hall 5.4. Street Cleaning (EPWP/CDW) 5.5. Sport Facilities | Sonop, Khalamtwana Regorogile, Sonop 1, Segwaelane, Khalamtwana |
| 3. Water & Sanitation | 3.1. Upgrading of sewerage/ sani- tation 3.2. Supply of Water | Vuka Section All Areas |  |  |  |  |
| 4. Roads & Storm water | 4.1. Building of Roads & Sidewalks 4.2. Gravelling and repaving of internal roads 4.3. Building of stormwater drains 4.4. Upgrading of existing drains (enlarging) | Mamogalieskraal and Vuka Section |  |  |  |  |
|  |  |  |  | EXCESS NEEDS |  |  |
|  |  |  |  | 6. LED | 6.1. Tourism site – “Legae la rona” and Apartheid Museum 6.2. Job Creation - Toilet making, Brick making, Welding, Piggery, Chicken Farm, Community Bakery, Food, security garden, Car wash and Agriculture and Farming project. 6.3. Skills Development Program 6.4. Market |  |
| 5. Social Services | 5.1. High School 5.2. Library 5.3. Rehabilitation Centre 5.4. Sports facilities | Elandsrand, Mamogalieskraal and Vuka Section |  |  |  |  |
|  |  |  |  | Social Services | 5.6. Upgrading of ablution block, building of class rooms and fencing 5.7. School hall at Pansdrift and Sonop Primary Schools 5.8. Revamping of Community crèche at Segwaelane 5.9. Feeding Scheme for Eldery/ Disabled - Sonop, Khalamtwana, Segwaelane – Tebogo Primary School 5.10. Building of new Clinic at Sonop |  |
| EXCESS NEEDS |  |  |  |  |  |  |
| 6. LED | 6.1. Youth Skills Development Centre 6.2. Hawkers Facilities 6.3. Agriculture Development | 6.4. Tourism Business Development 6.5. Business Complex 6.6. Transfer Station |  |  |  |  |
| WARD 40 |  |  |  |  |  |  |
| NEEDS | PROJECTS | AREAS |  |  |  |  |
| 1. Land & Housing | 1.1. Transfer to Madibeng 1.2. RDP & PHP Houses 1.3. Formalization of Informal Settlements 1.4. Upgrading of cemeteries | Sonop Regorogile, Sonop, Segwaelane, Khalamtwana Khalamtwana, Farm area, Regorogile, Pansdrift Sonop, Farm Area |  |  |  |  |
| 2. Electricity | 2.1. Household Electrification 2.2. High mast lights (14) 2.3. House wiring | Regorogile Phase 2, Farm area, Segwaelane, Sonop, Khalamtwana Regorogile, Sonop, Segwaelane, Khalam-twana, Sonop |  |  |  |  |

| WARD 41 |  |  |  |  |  |  |  |  | ANALYSIS OF WARD PRIORITY NEEDS |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| NEEDS |  | PROJECTS |  | AREAS |  |  |  |  |  |  |  |  |  |  |  |
| 1. Water & Sanitation |  | 1.1. Rehabilitation of Existing Sewage System 1.2. Yard Connection |  | All Sections |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | Water & Sanitation | Roads & Stormwater | Electricity | Land & Housing | Social Services | LED |
| 2. Electricity |  | 2.1. Household Connection 2.2. High Mast Lights (increase) |  | Moseja, Beverley Hills, Block E, Motseng and Midas |  |  |  |  | Priority 1 | 1, 2, 3, 4, 6, 8, 10, 12, 16, 24, 27, 28, 34, 35, 36, 41 | 5, 9, 11, 13, 15, 17, 18, 19, 20, 21, 23, 30, 32 | 37 | 7, 14, 22, 25, 26, 29, 31, 33, 38, 39, 40, |  |  |
| 3. Roads & Stormwater |  | 3.1. Regravelling & paving of Internal Roads 3.3. Stormwater drainage |  | All Sections Molefe Makinta Highway |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Priority 2 | 5, 7, 9, 18, 20, 21, 29, 30, 33, 37 | 1, 2, 4, 6, 12, 16, 22, 24, 25, 26, 27, 28, 31, 34, 35 | 10, 14, 15, 19, 32, 36, 38, 39, 40, 41 | 8, 11, 13, 17, | 3, 23, |  |
| 4. Land & Housing |  | 4.1. PHP Housing 4.2. Fencing of Cemetery |  | All Sections Block E |  |  |  |  |  |  |  |  |  |  |  |
| 5. Social Services |  | 5.1. Mobile Clinic 5.2. Sports Facilities |  | All Sections Block E & Moseja |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Priority 3 | 19, 32, 39, | 3, 7, 10, 14, 36, 37, 38, 40, 41 | 2, 8, 16, 17, 21, 22, 25, 26, 28, 29 | 9, 12, 18, 20, 24, 34, 35, | 1, 4, 5, 6, 11, 13, 27, 30, 31, | 15, 23, 33, |
| EXCESS NEEDS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 6. LED |  | 6.1. Agricultural Projects – All Sections |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Priority 4 | 14, 17, 22, 25, 31, 40, | 8, 39, | 1, 3, 6, 7, 9, 11, 20, 23, 24, 30, 33, 34, 35 | 2, 5, 10, 16, 19, 21, 27, 28, 32, 36, 37, 41 | 12, 15, 18, 29, 38, | 4, 13, 26, |
| - OUTCOME OF WARD PRIORITY NEEDS: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| RANKING | NEED |  |  | NO OF WARDS |  |  | Priority 5 | 26, 38, |  | 12, 13, 27, 31, | 1, 3, 4, 6, 15, 30, 36, | 8, 9, 10, 14, 16, 17, 19, 20, 21, 22, 23, 24, 25, 32, 33, 34, 35, 36, 37, 39, 40, 41 | 2, 5, 7, 11, 18, 28, 29, |
| Priority 1 | Water and Sanitation |  |  | 16 |  |  |  |  |  |  |  |  |  |
| Priority 2 | Roads and Stormwater |  |  | 15 |  |  |  |  |  |  |  |  |  |
| Priority 3 | Electricity |  |  | 10 |  |  |  |  |  |  |  |  |  |
| Priority 4 | Land and Housing |  |  | 12 |  |  |  |  |  |  |  |  |  |
| Priority 5 | Social Services |  |  | 22 |  |  |  |  |  |  |  |  |  |
| Priority 6 | Local Economic Development |  |  | 25 |  |  | Priority 6 | 11, 13, 15, | 29, | 4, 5, 18, |  | 2, 7, 26, 28, | 3, 8, 9, 12, 14, 16, 17, 19, 20, 21, 22, 24, 25, 27, 31, 32, 33, 34, 35, 36, 37, 38, 39, 40, 41 |
| DETERMINATION OF REVIEWED MUNICIPAL WIDE NEEDS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| At an IDP Representative Meeting held on 19 November 2019 the following needs were determined as Municipal Wide Needs |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

Priority 1      :    Water and Sanitation

Priority 2      :    Roads and Stormwater

Priority 3      :    Electricity

Priority 4      :    Land and Housing

Priority 5      :    Social Services

MUNICIPAL VISION, MISSION AND VALUES

Definition of a Vision:

A vision statement can be explained as a picture of your company in the future.  The vision statement should be your inspiration, the framework for all your strategic planning and ultimately an aim to work towards.  It is the answer to the question: “What do we want to achieve?  The Vision is a long term commitment and has to be realistic in the sense that it should be achievable.

The Local Municipality of Madibeng has reviewed its Vision and Mission at the IDP Representative Forum Meeting of the 11 March 2015

VISION

“MADIBENG, THE PROSPEROUS PLATINUM AND GREEN TOURISM CITY”

The Madibeng vision building blocks;

| PROSPEROUS | economically healthy and growing |
| --- | --- |
| GREEN | agriculture; natural beauty; water |
| PLATINUM | high value resource; mining |

Reposition, Rebranding and Renewal

The 5th Administration introduced new policy initiatives to fast track service delivery to the people of Bokone Bophirima. The RRR is anchored on five concretes which is aligned with the Municipal Vision in order to achieve green tourism city.

Difference between Vision and Mission:

The Vision statements is based on the future state of a company, whilst the Mission statement is focusing on the present state of the company

Definition of a Mission Statement

A mission statement expresses the company’s purpose for those in the organization as well as for the public.

MISSION

“WE, THE MADIBENG LOCAL MUNICIPALITY, ARE COMMITTED TO STRIVE TO REMAIN ACCOUNTABLE IN RENDERING AFFORDABLE QUALITATIVE AND SUSTAINABLE

SERVICES TO OUR COMMUNITY IN LINE WITH OUR CONSTITUTIONAL OBLIGATIONS”

VALUES

| TRANSPARENCY | (openness, honesty; information sharing and availability; clarity) |
| --- | --- |
| DISCIPLINE | (legal, moral and ethical self control; accountability for responsibilities) |
| INTEGRITY | (commitment, respect, true to self and even in absence of others) |
| ACCESSIBILITY | (to councilors, managers, facilities, services and information) |
| ACCOUNTABILITY | (responsibility) |
| PROFESSIONALISM | (time management, image and conduct) |
| VALUE FOR MONEY | (worthwhile; fair exchange) |
| COMMUNICATION | (quality information, timeously and in the right |

STRATEGIC OBJECTIVES

MUNICIPAL TRANSFORMATION AND INSTITUTIONAL DEVELOPMENT

Problem Statement Ineffective institution environment that led to poor corporate service, non-alignment of planning processes, non-compliance with regulations, poor monitoring, evaluation and reporting

OUTPUTS

DIRECT OUTCOME

ULTIMATE OUTCOME

OU

INTERMEDIATE OUTCOME

OU

HR Policies and procedures developed/reviewed by target date

WSP developed by target date

Improved Implementation of HR Policies and Procedures

% implementation of WSP

HR Strategy developed by target date

Invest in Human Capital

Increased implementation of HR Strategy

LLF Structures reinstated by target date

EE Plan developed by target date

Improved Effectiveness and Efficiency of Municipal Administration

Increased implementation of Competency Framework

Talent Mgt Strategy developed by target date

Recruitment and Retention Mgt Strategy developed by target date

Increased alignment of the Organisational Structure to the Strategy of the Municipality

Organisational structure reviewed by target date

Placement of staff completed by target date

Increased staff performance

Invest in ICT Infrastructure

% implementation of ICT Infrastructure

ICT policy governance framework developed by target date

Problem Statement Ineffective institution environment that led to poor corporate service, non-alignment of planning processes, non-compliance with regulations, poor monitoring, evaluation and reporting

OUTPUTS

DIRECT OUTCOME

ULTIMATE OUTCOME

OU

INTERMEDIATE OUTCOME

OU

IDP Process Plan developed by target date

IDP Status Quo Analysis developed by target date

Enhanced IDP/Budget/PMS Planning

IDP Projects/Integration developed/completed by target date

IDP & Budget aligned by target date

Project Management Framework developed by target date

Harmonized Planning, Implementation, Monitoring, Performance and Reporting System

Improved Planning, Monitoring, Evaluation and Reporting

Increased Implementation of Municipal Wide Project Management System

% of Municipal Projects registered on the PM System

PMS framework and Procedure Manual reviewed by target date

SDBIPs developed by target date

Annual Report developed by target date

Increased implementation of the Monitoring and Evaluation System

M&E System developed by target date

Performance Scorecards developed by target date

BASIC SERVICE DELIVERY AND INFRASTRUCTURE

Problem Statement: Inadequate and ineffective infrastructure due to poor leadership resulting in poor service delivery, rapid deterioration of infrastructure and increased civil disobedience

OUTPUTS

DIRECT OUTCOME

ULTIMATE OUTCOME

OU

INTERMEDIATE OUTCOME

OU

Rand Value of Capital sourced for Municipal Infrastructure

ML/MVA of bulk capacity

Improved Distribution of Municipal Engineering Services

% of households with provision of municipal services

% implementation of planning processes

% implementation of Smart metering Technology

# implementation of stakeholders engagement strategy

Enabled uninterrupted Access to Engineering Services

Reduced Water and Electricity Losses

Turn- around time to repair defects and defaulter cuts

Enhanced Provision of Sustainable Engineering Services to the Communities

Capacitated Planning Office and Project Management Units

% of MIG projects registered

% MIG projects completed on time, quality and budget

Empowered Planning of Municipal Engineering Infrastructure and Projects

Updated Integrated Engineering Services Plans

Integrated master plans/operational manuals/By Laws developed by target date

Uninterrupted Maintenance Programme

Sustainable maintenance capacity and self-reliance

Plant and equipment procured by target date

Maintenance plans developed by target date

Problem Statement: Inadequate and ineffective infrastructure due to poor leadership resulting in poor service delivery, rapid deterioration of infrastructure and increased civil disobedience

OUTPUTS

DIRECT OUTCOME

ULTIMATE OUTCOME

OU

INTERMEDIATE OUTCOME

OU

Response time for Businesses/ Urban /Rural/Specific Areas

Improved response time to emergencies and other municipal services

# of facilities complying to OHS and Building Regulations

Increased access to emergency services and other municipal services

Policies reviewed/developed by target dates

Increased implementation of Municipal policies and by-laws

By-Laws reviewed/ developed by target dates

Improved social infrastructure, protection and education outcomes

% implementation of the Safety strategy

Increased implementation of safety policies

% implementation of the Safety plan

Improved provision of safe, clean and healthy environment

Increased implementation of the environmental policies

% implementation of the environmental strategy

% implementation of the environmental plan

Education and Awareness Strategy and plans developed by target date

Increased implementation of Education and Awareness programmes

Number of education and awareness programmes developed

LOCAL ECONOMIC DEVELOPMENT

Problem Statement: The high rate of unemployment among youth, closing of industries due to the down spiralling in the economic performance, ineffective investment scheme, inefficient system on mining CSI approach, ineffective incentive scheme, equally impacted negatively in the development of SMMÉ’s, Poor performance in tourism, agricultural output which is a consequent failure in the socio economic growth of the Madibeng local municipality.

INTERMEDIATE OUTCOME

OU

ULTIMATE OUTCOME

OU

DIRECT OUTCOME

OUTPUTS

Increased promotion and support LED initiatives in line with set targets, norms and standards

Research on investment incentive scheme completed by target date

Formalised and capacitated street trading/informal traders

Stimulate tourism development and promotion

Increased capacitation and support provided to SMMEs

Increased implementation of the investment policy to attract and retain investments

# of registered street traders

Street/Informal Traders Strategy developed by target date

# of tourism events facilitated

# of initiatives implemented to increase tourists visiting Madibeng

# of Cooperatives empowered thrrough LED initiatives

# of SMMEs linked to established businesses

# of SMMEs supported through training

# of initiatives to attract and retain investment

Investment attraction policy developed by target date

Increased economic growth, enhanced tourism, Capacitated SMMEs and Well Administered Economic Activities

Problem Statement: The high rate of unemployment among youth, closing of industries due to the down spiralling in the economic performance, ineffective investment scheme, inefficient system on mining CSI approach, ineffective incentive scheme, equally impacted negatively in the development of SMMÉ’s, Poor performance in tourism, agricultural output which is a consequent failure in the socio economic growth of the Madibeng Local Municipality.

INTERMEDIATE OUTCOME

OU

ULTIMATE OUTCOME

OU

DIRECT OUTCOME

OUTPUTS

# of funded Municipal projects integrated in the SLP of mining houses

Increased implementation of the Small Town Regeneration Programme

# of projects facilitated on STR project

# of partnership agreements signed with local businesses

# of signed MOU’s with social-economic development partners

# of agricultural development projects facilitated

Business plan developed by target date

Feasibility study developed by target date

Improved implementation of CSI Projects with the Mining Industry as part of the SLP focusing on alignment of Municipal IDP Projects with the mines

# of SLP monitoring reports developed by target date

# of temporary jobs created through EPWP

Increased implementation of EPWP policy to increase jobs

Increased economic growth, enhanced tourism, Capacitated SMMEs and Well Administered Economic Activities

Increased Implementation of Madibeng brick factory

Increased promotion and support LED initiatives in line with set targets, norms and standards

Increased implementation of PPPs (Industrialization IDZ and Agriculture)

Problem Statement: The high rate of unemployment among youth, closing of industries due to the down spiralling in the economic performance, ineffective investment scheme, inefficient system on mining CSI approach, ineffective incentive scheme, equally impacted negatively in the development of SMMÉ’s, Poor performance in tourism, agricultural output which is a consequent failure in the socio economic growth of the Madibeng local municipality.

INTERMEDIATE OUTCOME

OU

ULTIMATE OUTCOME

OU

DIRECT OUTCOME

OUTPUTS

Research on Madibeng Vegetable Market developed by target date

Increased promotion and support LED initiatives in line with set targets, norms and standards

Increased implementation of Madibeng Vegetable Market to grow agriculture and food security

Integrated Contractor development strategy developed by target date

Incubation Centre developed by target date

Business Plan on Madibeng Vegetable Market developed by target date

# of Agricultural development projects facilitated

SMME Incubation Business Plan developed by target date

Increased implementation SMME incubation centre to support and develop emerging business

Increased economic growth, enhanced tourism, developed SMMEs and well administered Outdoor advertising

% Uptime for ICT Infrastructure

# of SMMEs accommodated in municipal centres

# of Contractor SMMEs supported through training

Increased Implementation of integrated contractor development strategy (ICDS) to rationalise SMME’s

# of Tourism workshops facilitated

MUNICIPAL FINANCIAL VIABILITY

Problem Statement: The Madibeng Local Municipality is not financially viable due to poor revenue collection, financial control, non-compliance to financial legislations and policies which prevents the municipality to deliver quality services

OUTPUTS

DIRECT OUTCOME

% of debt outstanding

ULTIMATE OUTCOME

OU

INTERMEDIATE OUTCOME

OU

Data cleansing conducted by target date

Improved Revenue Management

% accuracy of the indigent register

Budget developed by target date

Improved Budget Management

Improved Compliance to SCM Prescripts

SCM Plan developed by target date

Improved Municipal Financial Standing

% accuracy of spending on the budget

Improved Expenditure Management

% implementation of internal expenditure control measures

Improved Financial Viability and Audit Outcomes

Improved Asset Management

Stock take conducted by target date

% accuracy of the Asset Register

Improved Compliance to Reporting Requirements

# of reports compiled within specified time frames

Audit Action Plan developed by target date

Improved Audit Outcomes

Increased implementation of the Post Audit Plan

# of audit findings resolved y target date

GOOD GOVERNANCE AND PUBLIC PARTICIPATION

Problem statement: Poor governance due to inadequate and ineffective control environment and poor stakeholder relations.

OUTPUTS

DIRECT OUTCOME

ULTIMATE OUTCOME

OU

INTERMEDIATE OUTCOME

OU

Governance structures developed by target date

Improved functionality and existence of governance structures

# of Governance structures Meetings held

Improved Good Governance systems

Improved integrated planning

Integrated planning processes developed by target date

Fraud Prevention strategy reviewed target date

Reduced incidents of fraud and

corruption

Improved implementation of fraud prevention plans

Fraud Prevention plan reviewed target date

Improved confidence in the systems of Local Government

Risk Mgt framework reviewed by target date

Enhanced administrative systems in line with applicable legislation

Improved implementation of consequence management

Risk Mgt framework strategy reviewed by target date

Compliance checklist for all departments developed by target date

% of ill-discipline cases attended to

Improved compliance to applicable legislation

Increased stakeholder awareness on public participation

Stakeholder communication strategy developed by target date

Improved Public Participation in municipal processes

Improved community engagement on issues affecting them (Feedback)

% of Councillors trained on their role and responsibilities

SPATIAL RATIONALE

Problem Statement: Non availability of land and infrastructure results disintegrated, unsustainable and undesired developments

OUTPUTS

DIRECT OUTCOME

ULTIMATE OUTCOME

OU

INTERMEDIATE OUTCOME

OU

Land acquired by target date

SQM of Land Disposed by sector departs targets

Increased Township establishments (Greenfield programme)

Land audit conducted by target date

Land audit conducted by target date

Improved and conducive environment for human habitation

Increased formalisation of informal/rural settlements (Brownfield programmme)

% implementation of Wall to wall land use scheme

Increased Implementation of the SDF

SDF Reviewed by target date

Increased implementation of the  breaking new grounds strategy (BNG) and the municipal housing sector plan

Municipal Housing sector plan finalized by target date

Number of Houses handed over to communities

Integrated and Sustainable Human Settlement

Integrated Human settlement housing Models

PPP identified by target date

PPP agreements developed by target date

Increased Development through PPP

Reduced Land invasion and informal settlements

Increase utilization of the National Upgrade support plan

% compliance to National Upgrade Support Plan

% implementation Land invasion policy

Land Invasion Policy reviewed by target date

PPP Signed by target date

Reduced informal settlements

DEVELOPMENT STRATEGIES

MUNICIPAL TRANSFORMATION AND INSTITUTIONAL DEVELOPMENT

| PLANNING LEVEL | PLANNING STATEMENT | KPI | BASELINE | TARGET |  |
| --- | --- | --- | --- | --- | --- |
|  |  |  | Jun 2018 | 2019/20 | 2020/21 |
| Strategic Goal 1 | Improved Effectiveness and Efficiency of Municipal Administration |  |  |  |  |
| Strategic Obj 1.1 | Invest in Human Capital | % of training budget spent | 100% | 100% | 100% |
| Strategy 1.1.1 | Implementation of workplace skills programme | % Implementation of prioritized training programme | 100% | 100% | 100% |
| Strategy 1.1.2 | Adherence to Strategic Human Resource Plan | Review of Strategic Human Resource Plan | 1 | 1 | 1 |
| Strategic Obj 1.2 | Compliance to Employment Equity Plan | Review of Employment Equity Plan | 0 | 1 | 1 |
| Strategy 1.2.1 | Adherence to employment of equity target groups in highest level of management | Number of people from employment equity target groups employed in the three highest level of management | 0 | 4 | 4 |
| Strategy 1.2.2 | Review of HR Planning Policies | Number of HR Policies reviewed | 0 | 8 | 1 |
| Strategy 1.2.3 | Compliance to Employee Wellness Policy | Development of Employee Wellness Policy | 0 | 1 | 0 |
| Strategy 1.2.4 | Increase functionality of Section 79 Committee system | Number of reports on Functionality of Council and its Committees compiled and submitted to Council for adoption | 2 | 2 | 2 |
| Strategy 1.2.5 | Increased alignment of the Organizational Structure to the Strategy of the Municipality | Annually reviewed organizational structure aligned to the strategy of the municipality | 1 | 1 | 1 |
| Strategy 1.2.6 | Reduced vacancies in line with the identified critical posts on the new organisational structure | Number of Senior Management posts filled | 9 | 4 | 4 |
| Strategy 1.2.7 | Invest in ICT Infrastructure | Number of ICT Governance Framework reviewed | 1 | 1 | 0 |
| Strategy 1.2.8 | Ensure effective implementation of Council resolutions | Number of reports to SMT on implementation of Council resolutions | 4 | 4 | 4 |
| Strategy 1.2.9 |  | Number of Records Management Policy reviewed | 1 | 1 | 1 |
| Strategy 1.2.10 |  | Number of Municipal Delegaqtions of Authority reviewed | 1 | 1 | 1 |
| Strategic Obj 1.3 | Develop 5 year IDP (2021-2026) | Number of 5 Year IDP document developed by 31 May 2021 | 4 | 0 | 1 |
| Strategy 1.3.1 | Integrated intergovernmental relations and stakeholder consultation and partnerships | Number of partnership and collaboration established | 2 | 2 | 2 |
| Strategic Obj 1.4 | Improved level of corporate governance and compliance through efficient and effective standards, practices and systems | Number of risk profiles completed | 30 | 8 | 8 |
| Strategy 1.4.1 | Improved effectiveness of risk financing and transfer | Number of insurance audits undertaken | 4 | 4 | 4 |
| Strategy 1.4.2 | Finalise risk based audit reports and Performance audit reports as stipulated on the approved annual audit plan | Percentage of planned internal audit reviews completed | 90% | 90% | 90% |
| Strategy 1.4.3 | Finalised investigations of cases reported | Percentage of cases finalised with clear recommendations | 100% | 100% | 100% |
| Strategic Goal 2 | Improved Planning, Monitoring, Evaluation and Reporting |  |  |  |  |
| Strategic Obj 2.1 | Harmonized Planning, Implementation, Monitoring, Performance and Reporting System | No of Performance Management framework and Procedure Manual reviewed | 1 | 1 | 1 |
| Strategic Obj 2.2 | Submit the Mid-year S72 report to the Mayor | No of Mid-year budget and Performance assessment reports submitted to the Executive Mayor, Provincial Treasury and National treasury by 25 Jan | 1 | 1 | 1 |
| Strategy 2.2.1 | Enhanced IDP Planning | Number of 5 Year IDP process plans drafted and submitted to Council by 31 Aug | 4 | 0 | 1 |
| Strategy 2.2.2 | Increased Implementation of Municipal Wide Project Management System | Develop and update a Project Management database |  | 1 | 1 |

BASIC SERVICE DELIVERY AND INFRASTRUCTURE

| PLANNING LEVEL | PLANNING STATEMENT | KPI | BASELINE | TARGET |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Jun 2018 | 2019/20 | 2020/21 |  |
| Strategic Goal 3 | Enhanced Provision of Sustainable Engineering Services to the Communities |  |  |  |  |  |
| Strategic Obj 3.1 | Adherence to Municipal Policies and By-laws |  |  |  |  |  |
| Strategy 3.1.1 | Increased implementation of Municipal policies and by-laws | No of policies and by-laws reviewed by 30 June | 1 | 5 | 5 |  |
| Strategic Obj 3.2 | Provision and monitoring of electricity services |  |  |  |  |  |
| Strategy 3.2.1 | Monitoring energy loss | % reduction in electricity losses | 49% | <30 | <30% |  |
| Strategy 3.2.2 | Increased provision of public lighting (street lights) | Number of street lights lights energized | 1 600 | 15 | 0 |  |
| Strategy 3.2.3 | Increased provision of public lighting (high mast lights) | Number of high mast energized | 263 | 15 | 15 |  |
| Strategy 3.2.4 | Uninterrupted Maintenance Programme | % Adherence to maintenance programme | 100% | 100% | 100% |  |
| Strategic Obj 3.3 | Increase access to basic services |  |  |  |  |  |
| Strategy 3.3.1 S | Provision of access to basic level of electricity | No. of households with access to basic level of electricity | 6 333 | 6 833 | 7 333 |  |
| Strategy 3.3.2 | Provision of access to basic level of water | No of households with access to basic level of water | 1 500 | 2 633 | 3 766 |  |
| Strategy 3.3.3 | Provision of access to basic level of sanitation | No of households with access to basic level of sanitation | 1 500 | 1 500 | 2 100 |  |
| Strategy Obj .4 | Provision and monitoring of water services |  |  |  |  |  |
| Strategy 3.4.2. | Monitoring of unaccounted water supply | % reduction of water loss | 23% | <22 | <22 |  |
| Strategy Obj 3.5 | Provision and monitoring of sanitation services |  |  |  |  |  |
| Strategy 3.5.1 | Increased access to sanitation in Madibeng ito sanitation | No. of additional households in formal dwellings provided with sewer connections |  | 0 |  |  |
| Strategy 3.5.2 | Improve the effluent quality compliance | No. of wastewater treatment works complying with SANS 241 | 0 | 2 | 2 |  |
| Strategy Obj .6 | Improved provision of safe, clean and healthy environment |  |  |  |  |  |
| Strategy 3.6.1. | Review and Update the Air Quality Management Plan | Number of Air Quality Management Plan developed and approved | 0 | 1 | 1 |  |
| Strategy 3.6.2. | Increased compliance of landfill sites | % compliance to landfill sites permit conditions by 30 June | 100% | 55% | 65% |  |
| Strategy 3.6.3. | Increased provision of waste management services in line with the waste management services norms and standards. | Number of households with access to refuse removals services | 73 400 | 75 400 |  |  |
| Strategy 3.6.4. |  | No of households on valuation roll provided with weekly wolide wate removal service |  |  | 39 856 |  |
| Strategy 3.6.5. |  | Number of 240ℓ bins rolled – out in line with the mass roll out program | New | 10 000 | 0 |  |
| Strategy 3.6.6. |  | Number of Integrated Waste Management plan reviewed and adopted | 1 | 1 | 0 |  |
| Strategy 3.6.7. |  | No of Waste Recyclers formalised to do waste minimisation at Brits Transfer Station | 1 | 1 | 1 |  |
| Strategy 3.6.8. |  | Number of informal settlements with access to refuse removal through bulk container service services | 0 | 9 |  |  |
| Strategy 3.6.9. |  | Number of progress reports on rehabilitation of Toloane river submitted | 0 | 1 | 1 |  |
| PLANNING LEVEL | PLANNING STATEMENT | KPI | BASELINE | TARGET |  |  |
|  |  |  | Jun 2018 | 2019/20 | Jun 2018 |  |
| Strategic Goal 4 | Improved social infrastructure, protection and education outcomes |  |  |  |  |  |
| Strategic Ob 4.1 | Increase access to emergency services and other municipal services |  |  |  |  |  |
| Strategy 4.1.1 | Access to emergency services | % of fire incidents managed and responded to, as a proportion of total no. received | 100% | 100% | 100% |  |
| Strategy 4.1.2 |  | % of disaster incidents responded to, as a proportion of requests received | 100% | 100% | 100% |  |
| Strategy 4.1.3 | Improved response time to water and electricity queries | Reaction time to customer queries on Water and Electricity | 24 hrs | 24 hrs | 24 hrs |  |
| Strategy 4.1.4 | Reduction in By-law contraventions | No of programmes for By-laws enforcement | 1 |  | 4 |  |
| Strategy 4.1.5. | Provision of access to roads and maintenance | No of area (m2) of paved roads network maintained by 30 June |  | 12 000 m2 | 12 000 m2 |  |
| Strategic Obj 4.2 | Improved quality of life through sports and recreation initiatives |  |  |  |  |  |
| Strategy 4.2.1 | Improve the accessibility of information to communities | No of library grant business plan submitted by 30 June | 0 | 1 | 1 |  |
| Strategy 4.2.2 | Increase acess to safe and healthy environment | No of parks maintained by 30 June | 0 | 13 | 13 |  |
| Strategy 4.2.3 |  | No of cemeteries maintained by 30 June | 0 | 6 | 6 |  |
| Strategy 4.2.4 | Planning and execution of programs (Arts, Culture, Sport) | Number of sports, arts, culture and recreation activities conducted by 30 June | 0 | 5 | 5 |  |
| Strategic Ob 4.3. | % MIG projects implemented and completed on time, quality and budget |  |  |  |  |  |
| Strategy 4.3.1 | Monitoring of projects | No of MIG projects registered |  |  | 10 |  |
| Strategy 4.3.2 |  | % of MIG budget spent by 30 June |  |  | 100% |  |

LOCAL ECONOMIC DEVELOPMENT

| PLANNING LEVEL | PLANNING STATEMENT | KPI | BASELINE | TARGET |  |
| --- | --- | --- | --- | --- | --- |
|  |  |  | Jun 2018 | 2019/20 | 2020/21 |
| Strategic Goal 5 | Increased economic growth enhanced tourism, Capacitated SMMEs and Well Administered Economic Activities |  |  |  |  |
| Strategic Obj 5.1. | Increased promotion and support LED initiatives in line with set targets, norms and standards |  |  |  |  |
| Strategy 5.1.1 | Increase Marketing Initiatives In All Sectors for Local Economic Development and Growth | Number of marketing initiatives implemented | 4 | 4 | 4 |
| Strategy 5.1.2 | Increase EPWP job opportunities | Number of jobs created through LED initiatives, EPWP, CWP and capital projects | 1075 | 1200 | 1200 |
| Strategy 5.1.3 | Adherence to Street Trading Bylaws | Review of Street Trading Bylaws | 1 | 1 | 1 |
| Strategy 5.1.4 | Formalised and capacitated street trading/informal traders | Number of registered street traders | 100 | 100 | 100 |
| Strategy 5.1.5 | Improved implementation of CSI Projects with the Mining Industry as part of the SLP focusing on alignment of Municipal IDP Projects with the mines | Percentage of CSI/SLP projects implemented | 100% | 100% | 100% |
| Strategy 5.1.6 | Implementation of EPWP policy | No EPWP beneficiaries trained | 20 | 20 | 20 |
| Strategy 5.1.7 | Implementation of the Small Town Regeneration Programme | Progress on implementation of STR | 100% | 100% | 100% |
| Strategy 5.1.8 | Increase initiatives to promote tourism | Number of tourism events facilitated | New | 2 | 2 |
| Strategy 5.1.9 | Increased regulation of local businesses | Number of business licence processed and issued from applications received | 7 | 15 | 0 |
| Strategy 5.1.10 | Increased initiatives to attract investment | Number of initiatives to attract and retain investors | 1 | 2 | 0 |
| Strategy 5.1.11 | Facilitation of Madibeng Agricultural production and market in terms of food security | No. of Madibeng Agricultural projects and markets facilitated | 4 | 4 | 4 |
| Strategic Obj 5.2. | Capacitation and support provided to SMMEs |  |  |  |  |
| Strategy 5.2.1 | Support and development of emerging business | Number of SMME’s supported through training | 50 | 100 | 100 |
| Strategy 5.2.2 | Implementation of integrated contractor development strategy (ICDS) to rationalise SMME’s | Reports on implementation of ICD Strategy | 0 | 1 | 1 |

MUNICIPAL FINANCIAL VIABILITY

| PLANNING LEVEL | PLANNING STATEMENT | KPI | BASELINE | TARGETS |  |
| --- | --- | --- | --- | --- | --- |
|  |  |  | Jun 2018 | 2019/20 | 2020/21 |
| Strategic Goal 6 | Improved Financial Viability and Audit Outcomes |  |  |  |  |
| Strategic Obj 6.1 | Improved Financial Viability and Audit Outcomes | % of Audit Committee recommendations accepted and adopted by Council | 95% | 100% | 100% |
| Strategy 6.1.1 | Revenue enhancement through the property portfolio | Completeness in (%) of revenue generated from property rates |  |  | 100% |
| Strategy 6.1.2 | Update Indigent Register | % of all qualifying indigent registered by 30 June | 99% | 100% | 100% |
| Strategy 6.1.3 | Improved Budget Management | % of total operating Budget spent | 95% | 95% | 95% |
| Strategy 6.1.4 | Improved Revenue Management | % of total operating budget revenue raised by 30 June | 98% | 95% | 95% |
| Strategy 6.1.5 | Ensure financial sustainability | Revenue collected as a % of amount billed for the year | 93% | 93% | 93% |
| Strategy 6.1.6 | Improved Procurement Management | % of tenders completed within the valid period (90 days from date of closure of advert) | 85% | 100% | 100% |
| Strategy 6.1.7 | Adherence to Fleet Management Policy | % Curbing in fuel operating budget | 100% | 100% | 100% |
| Strategy 6.1.8 |  | % Curbing in vehicle operating budget | 100% | 100% | 100% |
| Strategy 6.1.9 | Disclose in Annual Financial Statements all deviations condoned by Council | Number of reports on all deviations submitted to Council | 4 | 4 | 4 |
| Strategy 6.1.10 | Submit the Draft Budget to IDP for inclusion and approval of Draft IDP document by Council by 31 March | Draft Budget approved by Council by 31 March | 1 | 1 | 1 |
| Strategy 6.1.11 | Submit Final Budget for inclusion and approval of Final IDP document by Council by 31 May | Final budget approved by Council by 31 May | 1 | 1 | 1 |
| Strategy 6.1.12 | Submit the Annual Financial Statements by 31 August to the Office of the Auditor-General | Annual Financial Statements submitted by 31 August | 1 | 1 | 1 |
| Strategy 6.1.13 | Improved Asset Management | Compilation of a GRAP Compliant Fixed Asset Register as at 30 June | 1 | 1 | 1 |
| Strategy 6.1.14 | Improved Compliance to Reporting Requirements | Adjustments Budget submitted to Council by 28 February | 1 | 1 | 1 |
| Strategy 6.1.15 | Qualified Audit Opinion achieved | Qualified Audit opinion | 1 | 1 | 1 |
| Strategy 3.4.11 | Implement all the Roads, storm water infrastructure capital projects measured quarterly in terms of the approved Capital Budget spent | Percentage of Capital Budget spent by 30 June | 100% | 100% | 100% |

GOOD GOVERNANCE AND PUBLIC PARTICIPATION

| PLANNING LEVEL | PLANNING STATEMENT | KPI | BASELINE | TARGETS |  |
| --- | --- | --- | --- | --- | --- |
|  |  |  | 2018/19 | 2019/20 | 2020/21 |
| Strategic Goal 7 | Improved confidence in the systems of Local Government |  |  |  |  |
| Strategic Obj 7.1 | Improved Good Governance systems | Capacity building programs for councillors implemented by 30 June | 1 | 2 | 2 |
| Strategy 7.1.1 | Improved functionality and existence of governance structures | Number of Reports on ward committee functionality submitted to Council | 4 | 4 | 4 |
| Strategic Obj 7.2 | Reduced incidents of fraud and corruption | % of formally reported fraud, theft and corruption investigations initiated within 30 days after receipt | 100% | 100% | 100% |
| Strategy 7.2.1 | Improved implementation of fraud prevention plans | % of implemented fraud prevention plans | 100% | 100% | 100% |
| Strategy 7.2.2 | Improved implementation of ethics and integrity framework | % of councillors who have declared their financial interests | 0 | 0 | 100% |
| Strategy 7.2.3 |  | % of administrative staff who have declared their financial interests | 0 | 0 | 100% |
| Strategic Obj 7.3 | Enhanced administrative systems in line with applicable legislation | % of policies reviewed | 100% | 100% | 100% |
| Strategy 7.3.1 | Improved implementation of consequence management | % of disciplinary cases reported and attended | 100% | 100% | 100% |
| Strategy 7.3.2 | Improved compliance to applicable legislation | % of adherence to legislated compliance | 100% | 100% | 100% |
| Strategic Obj 7.4 | Improved Public Participation in municipal processes | No of Public Participation Strategies developed | 0 | 1 | 1 |
| Strategy 7.4.1 | Increased stakeholder awareness on public participation | % Adherence to communication strategy | 100% | 100% | 100% |
| Strategy 7.4.2 | Improved community engagement on issues affecting them (Feedback) | Number of engagement meetings with community | 4 | 4 | 4 |

SPATIAL RATIONALE

| PLANNING LEVEL | PLANNING STATEMENT | KPI | BASELINE | TARGET |  |
| --- | --- | --- | --- | --- | --- |
|  |  |  | 2018/19 | 2019/20 | 2020/21 |
| Strategic Goal 8 | Integrated and sustainable Human Settlement |  |  |  |  |
| Strategic Obj 8.1 | Management of informal settlements | No of progress reports on formalization of informal settlements by 30 June | 4 | 4 | 4 |
| Strategy 8.1.1 | Monitoring and assessment of building constructions | No of days for assessment of building plans from date of submission | 30 | 30 | 30 |
| Strategy 8.1.2 |  | Percentage of building inspections conducted | 100% | 100% | 100% |
| Strategy 8.1.3 |  | Percentage of occupancy certificates issued | 100% | 100% | 100% |
| Strategy 8.1.4 | Increased Township establishments | No. of Municipal Township establishment applications approved | 1 | 2 | 2 |
| Strategy 8.1.5 | Approved by law | No of building control by-laws approved | 1 | 1 | 1 |
| Strategy 8.1.6 | Provision of Basic Services and Maintenance | No. of reports on title deeds transferred and issued to eligible beneficiaries | 4 | 4 | 4 |
| Strategy 8.1.7 | Administration of rental housing | Percentage of Municipal rental housing Administered | 100% | 100% | 100% |
| Strategy 8.1.8 |  | Percentage of Private disputes with tenants or landlords attended to | 100% | 100% | 100% |
| Strategy 8.1.9 | Administration of municipal land | Percentage of municipal land administration including lease or sale | 100% | 100% | 100% |
| Strategy 8.1.10 | Land acquired for municipal developments | No of reports on acquisition of land | 4 | 4 | 4 |
| Strategic Obj 8.2 | Integrated Human settlement housing Models/ | No. of reports on low cost housing provided | 4 | 4 | 4 |
| Strategy 8.2.1 | Increased monitoring of the breaking new grounds strategy | % monitoring of Housing Sector Plan | 100% | 100% | 100% |
| Strategic Obj 8.3 | Land invasion and informal settlements curbing | % of land invasion and informal settlements attended to | 100% | 100% | 100% |
| Strategy 8.3.1 | Provision of land proclaimed | No of reports on portion of land transferred to the Municipality | 4 | 4 | 4 |
| Strategy 8.3.2 | Improved and controlled construction of buildings | No of days (90) for attending building contraventions from date of submission | 90 | 90 | 90 |
| Strategy 8.3.3 | Final Zoning Scheme (Land Use Management System) developed and submitted to Mayoral Co | No of Madibeng Land use Scheme developed submitted to Council for approval | 1 | 1 | 0 |
| Strategy 8.3.4 | Land Use applications processed | % of land Use applications processed | 100% | 100% | 100% |

MID TERM MUNICIPAL PERFORMANCE REPORT

The purpose of the report is to account to the public on the 2019/2020 mid-year institutional performance of Madibeng Local Municipality.

This report contains information which is based on the Service Delivery and Budget Implementation Plan (SDBIP) formulated for the financial year 2019/2020 and is based on the first and second quarter performance information.  It focuses on both financial and service delivery performance (non-financial) assessment.

This reporting is required through:-

- Local Government: Municipal Systems Act, Act no. 32 of 2000 as amended (referred to herein as MSA)

- Local Government: Municipal Financial management Act, Act no 56 of 2003 (referred to herein as MFMA)

- Madibeng Municipality reports on for the institutional performance relating to 2019/2020 financial year.

- Section 72 of the MFMA requires that the accounting officer of a municipality must by 25 January of every year assess the performance of the Municipality during the first half of the financial year, where after, the Mayor must table the report before 31 January each year.

- MFMA section 72(1) (a) (iii) requires the accounting officer to assess the performance of a municipality during the first half of the financial year, taking into account the past year’s annual report and progress on resolving problems identified in the annual report.

OUTCOME OF ORGANIZATIONAL PERFORMANCE AS AT 31 JANUARY 2020

| DIRECTORATE | Total targets per report | Not targeted | Total actual targets | AUDITED PERFORMANCE RESULTS |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Targets achieved | Targets not achieved | Overall (%) |
| Office of the Municipal Manager | 10 | 2 | 8 | 4 | 4 | 65.62% |
| Corporate Support Services | 18 | 8 | 10 | 6 | 4 | 72.80% |
| Community Safety | 7 | 2 | 5 | 2 | 3 | 60.90% |
| Public Safety, Facility & Fleet Management | 4 | 0 | 4 | 3 | 1 | 75.00% |
| Infrastructure and Technical Services | 7 | 5 | 2 | 0 | 2 | 0.00% |
| Local Economic Development | 11 | 1 | 10 | 7 | 3 | 70.00% |
| Planning and Human Settlement | 13 | 2 | 11 | 10 | 1 | 90.91% |
| Budget and Treasury Office | 10 | 2 | 8 | 1 | 7 | 63.64% |
| ORGANIZATIONAL PERFORMANCE | 80 | 22 | 58 | 33 | 23 | 62.35% |

Madibeng Local Municipality was placed under Administration as per Section 139(b) of the Constitution, (Act 108 of 1996) on 05 July 2019.

The Terms of Reference of the Intervention is set out below:

TERMS OF REFERENCE OF INTERVENTION AS PER SECTION 139(b) OF THE CONSTITUTION (ACT 108 OF 1996)

| Terms of Reference | Status at 30 June 2019 | Progress To Date | Further Action |
| --- | --- | --- | --- |
| Advise on the role of the Municipal Council vis-à-vis the Administrator [the Intervention team] during the intervention [decision making processes, public participation etc]; 4.3 (f) of the TOR | - Dysfunctional council, and its committees including LLF Poor Oversight on administration | Council, Mayoral Committee and other committees are functional Audit Committee presented report to council LLF functional | Training on roles Sanctioning of councilors for non-attend council and PC Meetings Targeted training of LLF Increased oversight on Post Audit Action Plan |
| Advise on the role of the Municipal Manager and the Administrator [with the Intervention Team] during the intervention [delegation of authority and administrative decision making processes] | No clear role between administration and intervention team No clear roles between council and Intervention team | Roles clarified Communication and decision making protocol between Troika, Mayoral Committee and council clarified | Appointment of MM, and other directors |
| Assess the relations between council and communities [e.g. community concerns against alleged corruption, maladministration, poor service delivery etc] | Poor relations between council and Community No structured engagements with communities Negative perception of council | Held engagements with stakeholder groups (Farmers, BIA, business Forums, Mining Houses, Service providers) Supported IDP consultations | Engagements with stakeholders Resuscitation of IGR structures Address ward committee concerns Improve communication |
| Effectiveness and capability of management [senior, middle, and junior management]; Supervise personnel and monitor municipal programmes | Lack of management capabilities High turnover of senior managers Low staff morale and ill-discipline (Ethics and Risk Survey) | External Acting Management appointments Effected Various Directorates engaged General Staff meeting convened Ethics and Risk Survey Findings presented to Council | Appointment of capable Senior Managers Directorates meetings convened regularly Continuous implementation of the Ethics and Risk Survey Conduct employee satisfaction survey |

| Terms of Reference | Status at 30 June 2019 | Progress To Date | Further Action |
| --- | --- | --- | --- |
| Compliance to policies and regulations [e.g. recruitment policies, employment equity etc]; Status on recruitment [structure, filling of posts etc]; | General Non-compliance with policies and regulations, e.g. deliberate disregard of requirements of Section 56 and 57 Managers Un-approved Organisational Structure Bloated and unfunded Organisational Structure Irregular appointments High vacancy rate for critical positions | Review of Actions that are non-compliant to Policies and Regulations Implemented Risk and Ethics Management Framework Appointed Ethics and Risk Champions Continuous engagement with labour | Regularisation and placement of affected staff Re-skilling and training of affected staff to avoid further appointments Filling of key and critical posts (skills based) Conduct further training on roles and functions of Councillors and Officials on appointment of personnel |
| Assess the seriousness of the financial problem in the Municipality | Non-Cash Funded Budget Cash Flow UIF and W Expenditure Tenderisation (over-dependence on service providers) of BTO Abuse of Regulation 32 Non-communication with service provided High expenditure on non-service delivery contracts | Reduction of the budget Compilation of UIF & W Registers Engagement with BTO Service Providers over Value For Money Submitted Contract Management Register to Provincial Treasury No regulation 32 procurements Assessment of non-essential (unaffordable) contracts (Fuel, fleet and IT) | Reduction of the R360m deficit stability of Cash Flow Training on Financial Policies and Procedures Consequence Management on UIF & W Capacity Building of Councillors on roles and responsibilities relating to SCM & oversight responsibilities Review and termination of unaffordable contracts |
| Oversee and facilitate the development and implementation of the Financial Recovery Plan as drafted with the assistance of National Treasury | Non-compliance with directive on preparation of Financial Recovery Plan (FRP) | Financial Recovery Plan has been approved by Council together with Special Adjustment Budget Approved Financial Recovery Plan submitted to Provincial Treasury | Further engagement with Provincial and National Treasury on reduction/elimination on the deficit Continuous monitoring on the implementation of the FRP Quarterly reports to Council |

| Terms of Reference | Status at 30 June 2019 | Progress To Date | Further Action |
| --- | --- | --- | --- |
| Improve internal control environment | Poor internal control systems Inadequate Financial Policies and Procedures Poor work ethics Compromised SCM integrity Poor/non-existence records management systems Under-utilisation of IT System | Interim Internal Controls established BTO Official addressed on Integrity issues Engagement with Solar System service provider to improve functionality of the system Re-organised SCM Committees | Development of Financial Policies and Procedures Development of Standard Operating Procedures on: Contract Management Payment of Suppliers within 30 days SCM and Journals Records Management Systems |
| Ensure all monthly reconciliations are done and cleared timeously | Bank Reconciliations not done Illegal Debit Orders Creditors Reconciliations not done Debtors Reconciliations not done | Bank Reconciliation conducted but still inefficiencies identified Continuous identification of illegal debit orders | Creditors Reconciliations to be done on Weekly Basis Debtors Reconciliations to be done on Weekly Basis Continuous monitoring and reversal of illegal debit orders |
| Recommend appropriate changes to the municipality’s operations, structure; processes, policies, bylaws, budget, expenditure and revenue-raising measures; | High debtors book -R2b Ad hoc revenue enhancement and debt collection Councillors and officials owe municipal services No proper engagement/Contractual relations with bulk creditors/debtors | Revenue enhancement plan Debtors age analysis compiled Measures in place to raise revenue (short term strategies in place) , integration of systems to improve budgeting and expenditure Payment arrangement concluded with bulk creditors, i.e. ESKOM, Magalies Water, and Rand Water to repay their debt | Implementation of revenue enhancement and Debt collection plan To recover debt from staff and councillors Adherence to payment plans commitments with bulk creditors, such as ESKOM, Tshwane, Rand-Water, and Magalies Water Feasibility of taking over electricity reticulation from Tshwane in Hartbeespoort and surrounding areas |

| Terms of Reference | Status at 30 June 2019 | Progress To Date | Further Action |
| --- | --- | --- | --- |
| To guide and support procurement processes for service related to MIG and PIG funded projects in an efficient and effective manner within the existing legal provisions and policies of the Municipality | The Municipality has lost R156 million on MIG due to poor performance on project and contract management Late appointment of service providers | 5 out of 6 water and sanitation project appointed for construction 7 roads projects appointed Finalise all outstanding arrangement (Guaranties, Sureties, Insurance and Safety Files, Site handover and negotiations | Monthly Contractor performance reporting forum Proactive registration of projects on the MIG MIS Procurement plans for 2020/2021 |
| To provide technical and project management support in the implementation of MIG, DWS,WSIG,INEP and PIG funded projects To provide support in the management of service providers in MIG and PIG funded projects to ensure delivery | Delay in appointment of service providers Litigation by service providers who were in the Panel Poor contract management Project stoppage by communities | Application by contractors on the panel was dismissed by Court of Law Functionality and effectiveness of SCM committees was addressed Improved coordination during project handovers with the PSC, Cllr, CLO | Expeditious certification by MISA and COGTA to expedite expenditure SCM Training Hold monthly contractors performance forum Facilitate continuous engagement with various stakeholders |
| To oversee and support contract management processes | Poor project management Late payment of service providers Failure to pay service providers in time | Developed project register and conducted monthly review of the implementation plan Creditors register completed | Monitoring and reporting to ensure that the projects are completed in time, budget and scope |
| Guide and support procurement processes for services related to MIG and PIG funded projects in an efficient and effective manner within the existing legal provisions and policies of the Municipality | Irregular appointment of some service providers LSO (Draught Relief) and Sogika Consulting Engineers (DWS infrastructure Backlog) | Termination of some irregular appointments has been effected Consequence management for affected officials is enlisted in the 15 immediate action list Directive issued for Procurement plans | Verification reports on work done to be completed Disciplinary action in line with the 15 immediate priority plan Enforcement of procurement practices strictly according to procurement plans |
| Management and technical support in the SMME development and EPWP implementation | No SMME development support EPWP is implemented but not centralized | SMME database and development program to council for approval Centralising implementation of EPWP to one Department | SMME data base approval Centralised EPWP coordination approval in consultation with DPWR |
| Terms of Reference | Status at 30 June 2019 | Progress To Date | Further Action |
| To facilitate the quality of services [water quality, sewer overflow, sanitation services, electricity, internal roads and Stormwater drainage] | Poor quality of water due to non-timeous maintenance Intermittent supply of water and electricity due to over demand and limited supply Lack of payment for water and electricity by consumers | Water Quality improved through plant maintenance Pump Stations refurbishment plan Roads and Stormwater maintenance plan Facilitated the finalisation of Electricity Master Plan Developed electricity urgent maintenance plan for all substations for substations | Consider budget re-prioritisation during Budget Adjustment meeting Scheduled maintenance program with funding Pursue partnership with DBSA and other funders for development of water and sanitation master plan Maximise use of own resources for basic road maintenance |
| Strategic advice to the Municipality on various other issues, particularly in the service delivery aspects. | Outsourced all service delivery capacity No complaints handling system No approved service standards Multiple losses of potential revenue due to - Electricity illegal connections - Water illegal connections - Non-payment of services - Aged infrastructure - Vandalism of municipal assets and public infrastructure | Completed audit of Municipal fleet vs rental fleet Finalised costed audit report on fleet contract Revenue enhancement Cost curtailment (e.g. overtime) Revenue enhancement plan and activity plan approved by Council | Insourcing of certain functions Finalise alternative fuel supply with Municipal Banks Ring-fence budget for key revenue drive on infrastructure Development of service standards charter in line LG charter Development of comprehensive customer service turnaround in line with Council policy Community engagements to deal with challenges identified |
| Legal-related matters of the municipality (litigations, court orders, disciplinary cases, etc.) | Litigation against the Municipality mainly on allegations of breach of contract and non-payment Municipality Legal Unit did not play its role in both advisory services and quality control of SLAs The Unit was also not involved on potential and actual Labour Disputes | Litigation Register has been compiled Possible settlement agreements on certain matters underway based on Value for Money and legality Head of Legal now forms part of the Top Management All contracts/SLAs and legal matters are subjected to Legal Unit for quality control | Pro-active engagement on all legal matters including Labour and Contracts Regular reports to the Audit Committee and council on Contingent Liabilities |
| Terms of Reference | Status at 30 June 2019 | Progress To Date | Further Action |
| Outcome of the forensic investigations conducted | A number of Forensic Investigations were conducted by Movundlela Consulting Provincial Treasury conducted an investigations on unlawfully invested with the VBS Mutual Bank Current investigations (following Presidential proclamation) by SIU and DPCI | Final draft Forensic reports were received in September 2019 Efforts to present all the reports to the Audit Committee and subsequently to Council are at an advanced stage Briefing meetings with the SIU (Fleet and IT contracts) and the the DPCI (IT contracts) | Special Audit Committee and Council to be convened to consider all forensic reports SIU May extend proclamation to include other reported matters Consider recommendations of the SIU and DPCI on: - Termination of unlawful contracts - Disciplinary or criminal processes of implicated officials and Councilors |
| Status of disciplinary processes | Prolonged disciplinary cases Abuse/Inconsistent application of disciplinary processes | Reports on all outstanding cases Settlement of disciplinary cases in deserving cases Finalized report on absentee employees/ abscondment List of possible employees involved in irregular appointments and expenditure | Setup capable panels for management of disciplinary hearings Immediate focus on capacitation of Labour Relation Unit Referral of all instances of financial misconduct to Disciplinary Board |
| Processes on the alienation and sale of municipal land | There are allegations of irregular alienation of municipal land/ properties | Information gathering and verification of source of complaints ongoing | Update of municipal land register and immovable assets Audit of basic occupancy of municipal assets |